| PART 1 - GENERAL |  |
| --- | --- |
| 1.1 RELATED SECTIONS | .1 All sections and divisions. |
| 1.2 ADMINISTRATIVE | .1 Submit to Owner, Owner’s Advisor, and Design-Builder’s Consultants reviewed and approved submittals listed for review. Submit promptly and in orderly sequence to not cause delay in Work. Failure to submit in ample time is not considered sufficient reason for extension of Contract Time and no claim for extension by reason of such default will be allowed. .2 Do not proceed with Work affected by submittal until review is complete. .3 Present designs, calculations, quantities, shop drawings, product data, samples and mock-ups in SI Metric units. .4 Where items or information is not produced in SI Metric units converted values are acceptable. .5 Review submittals prior to submission to the Owner and Owner’s Advisor. This review represents that necessary requirements have been determined and verified, or will be, and that each submittal has been checked and co-ordinated with requirements of Work and Contract Documents. Submittals not stamped, signed, dated and identified as to specific project will be returned without being examined and considered rejected. .6 Notify the Owner and the Owner’s Advisor, in writing at time of submission, identifying deviations from requirements of Contract Documents stating reasons for deviations. .7 Verify field measurements and affected adjacent Work are co-ordinated. .8 The Design-Builder’s responsibility for errors and omissions in submission is not relieved by the Owner’s or Owner’s Advisor’s review of submittals. .9 The Design-Builder’s responsibility for deviations in submission from requirements of Contract Documents is not relieved by the Owner’s or Owner’s Advisor’s review. .10 Keep one reviewed copy of each submission on site. |
| 1.3 DESIGNS | .1 Submit to the Owner, Owner’s Advisor, and Consultants a copy of the Design-Builder’s approved designs, drawings and supporting calculations, details and documentation for review. Submissions shall be made at the following stages of the design process and include the information noted below as a minimum. .1 33% design stage: Submission shall include the following requirements as a minimum: .1 Drawings including plans, sections, details, elevations and flow diagrams or single line diagrams for all systems and elements of the building. .2 Schedules of equipment and finishes. .3 Specification drafts. .4 Indicative Capital Cost Estimate accurate to a Class C (+/-15%). .5 Copies of calculations of load, flow rates, pressure, and energy requirements. .6 LEED® Scorecard and Supporting documentation to demonstrate LEED® silver certifiable design. .2 66% design stage: .1 Drawings including plans, sections, details, elevations and flow diagrams or single line diagrams for all systems and elements of the building. .2 Schedules of equipment and finishes. .3 Specification drafts. .4 Substantive Capital Cost Estimate accurate to a Class B (+/-10%). .5 Life Cycle Cost Analysis. .6 Maintenance estimates and operating cost estimates per year of operation ($2010). .7 Copies of calculations of load, flow rates, pressure, and energy requirements. .8 LEED® Scorecard and Supporting documentation to demonstrate LEED® silver certifiable design. .3 Construction Document submission stage (design complete): .1 Drawings including plans, sections, details, elevations and flow diagrams or single line diagrams for all systems and elements of the building. .2 Schedules of equipment and finishes. .3 Specification. .4 Guaranteed Price not to exceed proponent’s originally offered costs. .5 Life Cycle Cost Analysis. .6 Maintenance costs and operating costs per year of operation ($2011). .7 Copies of calculations of load, flow rates, pressure, and energy requirements. .8 LEED® Scorecard and Supporting documentation to demonstrate LEED® silver certifiable design. |
| 1.4 SHOP DRAWINGS AND PRODUCT DATA | .1 Refer to CCDC 14-2000 GC 3.10 provisions. .2 The term "shop drawings" means drawings, diagrams, illustrations, schedules, performance charts, brochures and other data which are to be provided by Contractor to illustrate details of a portion of Work. .3 Submit shop drawings bearing stamp and signature of qualified professional engineer or architect registered or licensed in Province of Manitoba, Canada. .4 Indicate materials, methods of construction and attachment or anchorage, erection diagrams, connections, explanatory notes and other information necessary for completion of Work. Where articles or equipment attach or connect to other articles or equipment, indicate that such items have been co-ordinated, regardless of Section under which adjacent items will be supplied and installed. Indicate cross references to design drawings and specifications. .5 Allow 10 business days for Owner’s and Owner’s Advisor’s Engineer’s review of each submission. .6 Adjustments made on shop drawings by Owner or Owner’s Advisor are not intended to change Contract Price. If adjustments affect value of Work, state such in writing to Consultant, Owner and Owner’s Advisor prior to proceeding with Work. .7 Make changes in shop drawings as the Owner and Owner’s Advisor may require, consistent with Contract Documents. When resubmitting, notify the Consultant, Owner and Owner’s Advisor in writing of revisions other than those requested. .8 Accompany submissions with transmittal letter, in triplicate, containing: .1 Date. .2 Project title and number. .3 Contractor's name and address. .4 Identification and quantity of each shop drawing, product data and sample. .5 Other pertinent data. .9 Submissions include: .1 Date and revision dates. .2 Project title and number. .3 Name and address of: .1 Subcontractor. .2 Supplier. .3 Manufacturer. .4 Contractor's stamp, signed by Contractor's authorized representative certifying approval of submissions, verification of field measurements and compliance with Contract Documents. .5 Details of appropriate portions of Work as applicable: .1 Fabrication. .2 Layout, showing dimensions, including identified field dimensions, and clearances. .3 Setting or erection details. .4 Capacities. .5 Performance characteristics. .6 Standards. .7 Operating weight. .8 Wiring diagrams. .9 Single line and schematic diagrams. .10 Relationship to adjacent work. .10 After the Owner and Owner’s Advisor’s Engineer's review, distribute copies. .11 Submit one transparency or hard copy print bearing seals, stamp, date and signature and an electronic copy of shop drawings for each requirement requested in specification Sections and as the Owner and the Owner’s Advisor may reasonably request. .12 Submit an electronic copy and 6 hard copies of product data sheets or brochures for requirements requested in specification Sections and as requested by the Owner and/or the Owner’s Advisor where shop drawings will not be prepared due to standardized manufacture of product. .13 Submit an electronic and 6 hard copies of test reports for requirements requested in specification Sections and as requested by the Owner and/or the Owner’s Advisor. .1 Report signed by authorized official of testing laboratory that material, product or system identical to material, product or system to be provided has been tested in accord with specified requirements. .2 Testing must have been within two years of date of contract award for project. .14 Submit an electronic and 2 hard copies of certificates for requirements requested in specification Sections and as requested by the Owner and/or the Owner’s Advisor. .1 Statements printed on manufacturer's letterhead and signed by responsible officials of manufacturer of product, system or material attesting that product, system or material meets specification requirements. .2 Certificates must be dated after award of project contract complete with project name. .15 Submit an electronic and 4 hard copies of manufacturers instructions for requirements requested in specification Sections and as requested by the Owner and/or the Owner’s Advisor. .1 Pre-printed material describing installation of product, system or material, including special notices and Material Safety Data Sheets concerning impedances, hazards and safety precautions. .16 Submit an electronic and 4 hard copies of Manufacturer's Field Reports for requirements requested in specification Sections and as requested by the Owner and/or the Owner’s Advisor. .1 Documentation of the testing and verification actions taken by manufacturer's representative to confirm compliance with manufacturer's standards or instructions. .17 Submit and electronic and 4 hard copies of Operation and Maintenance Data for requirements requested in specification Sections and as requested by the Owner and/or the Owner’s Advisor. .18 Delete information not applicable to project. .19 Supplement standard information to provide details applicable to project. .20 If upon review by the Owner and the Owner’s Advisor, no errors or omissions are discovered or if only minor corrections are made, transparency (if provided) and one hard transparency copy will be returned and fabrication and installation of Work may proceed. If shop drawings are rejected, noted copy will be returned and resubmission of corrected shop drawings, through same procedure indicated above, must be performed before fabrication and installation of Work may proceed. |
| 1.5 SAMPLES | .1 Submit for review samples in duplicate as requested in respective specification Sections. Label samples with origin and intended use. .2 Deliver samples prepaid to Owner’s Advisor’s business address. .3 Notify Consultant, Owner and Owner’s Advisor in writing, at time of submission of deviations in samples from requirements of Contract Documents. .4 Where colour, pattern or texture is criterion, submit full range of samples. .5 Adjustments made on samples by the Owner and/or the Owner’s Advisor are not intended to change Contract Price. If adjustments affect value of Work, state such in writing to the Consultant, the Owner, and the Owner’s Advisor prior to proceeding with Work. .6 Make changes in samples which the Owner and/or the Owner’s Advisor may require, consistent with Contract Documents. .7 Reviewed and accepted samples will become standard of workmanship and material against which installed Work will be verified. |
| 1.6 CERTIFICATES AND TRANSCRIPTS | .1 Immediately after award of Contract, submit Workers' Compensation Board status. .2 Submit transcription of insurance immediately after award of Contract. |
| PART 2 - PRODUCTS |  |
| 2.1 NOT USED | .1 Not Used. |
| PART 3 - EXECUTION |  |
| 3.1 NOT USED | .1 Not Used. |