## Submittal List
Appendix F - Submittal Checklist
The following submittal checklist is not purported to be complete and is provided for reference only.
Section | Submission | Item | Description | Section
Bid/ Scheduling | Project Schedule |  | Submit within twenty (20) Business days of Award of Contract. | 01 32 16
| Commissioning Schedule |  | Submit to Contract Administrator at the same time as the Project Schedule. | 01 91 31
| Commissioning Plan |  | Submit within 18 weeks of award of Contract or earlier if required by Contractor’s Project Schedule. | 01 91 31
Planning of Work | Safety Representative |  | Submit in writing to the Contract Administrator the identity of the Contractor representative responsible for safety on Site | 01 35 29
| Product Data | UV Equipment | Provide Manufacturer's printed product literature and datasheets for the modified UV disinfection system, and include product characteristics, performance criteria, physical size, finish, and limitations. | 46 66 23
| Shop Drawings | UV Equipment | Shop Drawings showing the modifications to the existing system including general arrangements and layouts, overall dimensions, connection and mounting details, cross-sections, make and model numbers, and a complete materials list indicating the new components. Include Specifications, catalogue cuts, and descriptive literature. Include control panel drawings, power supply drawings, electrical and control schematics and diagrams. Provide information for all modified components [as specified in Section 46 66 23]. | 46 66 23
| Wiring Diagrams and Installation Details | Electrical | Submit wiring diagrams and installation details of equipment indicating proposed location, layout and arrangement, control panels, accessories, piping, ductwork, and other items that must be shown to ensure coordinated installation. | 26 05 01
| Shop Drawings and Product Data | Hangers and Supports for Electrical Systems | Provide manufacturer’s printed product literature and datasheets. Indicate connection details. | 26 05 29
| Shop Drawings and Product Data | Splitters, Junction Boxes, Pull Boxes, and Cabinets | Provide manufacturer’s printed product literature and datasheets. Indicate all wiring and connection details. | 26 05 31
| Shop Drawings and Product Data | Cable Trays | Submit Shop Drawings and Product data in accordance with 01 33 00 – Submittal Procedures and this Specification. | 26 05 36
| Design Drawings and Calculations | Cable Trays | For new cable tray only, prior to construction, submit design drawings and calculations indicating all tray loading has been reviewed by and bear the stamp of a Professional Engineer registered in the Province of Manitoba. | 26 05 36
| Product Data | Moulded Case Circuit Breakers | Submit product data in accordance with Section 01 33 00 – Submittal Procedures and include time-current current characteristic curves for breakers with minimum symmetrical (rms) interrupting capacity as shown at and over system voltage. | 26 28 21
| Product Data and Spare Parts | Disconnect Switches | Submit spare parts and manufacturer’s printed product literature, specifications, and datasheets. Include product characteristics, performance criteria, enclosure rating, and limitations. | 26 28 23
| Information | Instrumentation | Submit programming and configuration information as information only submittals. Minimum software documentation includes detailed operating description, flow charts, screen dumps or other information that describes the functionality of the program. | 40 05 00
| Shop Drawings and Product Data | Instrumentation | Submit Instrumentation and Control Panel Shop Drawings and technical information for all products/devices/components supplied. | 40 05 00
| Product Data | Fibre Optic Cabling | Submit product data in accordance with Section 01 33 00 – Submittal Procedures and Division 40. Submissions shall include manufacturers catalog and product literature, installation guidelines, and fibre optic patch panels. | 40 66 33
| Shop Drawings | Fibre Optic Cabling | Shop Drawings: Provide Termination drawings with complete list of materials and nameplate engraving list. Provide Interconnection wiring diagrams for the complete system showing every fibre in each cable | 40 66 33
| Design Drawings | Instrumentation | Provide design Drawings, PLC/HMI/SCADA programming, based on the Schneider M580 ePAC PLC system. Include control panel drawings, power supply drawings, electrical and control schematics and diagrams. | 40 70 00
| SCADA Interface Document | Instrumentation | Provide SCADA Interface Document, minimizing changes to the extent possible. | 40 70 00
| Safe Work Procedure (SWP) |  | Develop a Safe Work Procedure (SWP) for confined space entry with assistance from the City. Submit to Contract Administrator for approval at least twenty (20) Business Days prior to performing any confined space entry. | 01 65 00
| Work Plan |  | Submit a detailed work plan for any scaffolding, rigging, hoisting, and other similar services. The work plan shall include the proposed work performed, construction sequence, specialized equipment, and methods/procedures for all testing. | 26 05 01
| Lifting Plan |  | A lifting plan for all piping and equipment lifts shall be developed by a Professional Engineer registered in Manitoba. The lifting plan shall include, at minimum, the approximate weight of the item to be lifted, lifting mechanism, and capacity of the proposed lifting equipment. The lifting plan is to be submitted to the Contract Administer for review at least ten (10) Business Days prior to performing any lifts. All lifts are to be performed by qualified operators. | 01 65 00
Equipment Supply | Notice | All | Ten (10) Business Days before delivery, notice shall be given to the Contract Administrator so that arrangements for receipt and inspection can be made. | 01 66 10
| Form 100 | All | When the Contractor accepts the equipment delivery, they shall certify the delivery by completing Form 100 – Certificate of Equipment Delivery, attached to this specification. | 01 66 10
| Maintenance Tool Inventory | All | Maintenance Tools: Receive and catalogue items. Submit inventory listing to the Contract Administrator. Include approved listings in the operating and maintenance manual. | 01 78 00
| Spare Part Inventory | UV Equipment | In addition, the Contractor shall provide a list of all spare parts, not including lubricants, which normally would be required through the first five (5) years of operation. Provide prices for each part, guaranteed for six (6) months. | 46 21 00
Installation | Safety Orientation |  | Submit, by presentation to the Contract Administrator, the safety orientation for all Contractor’s Personnel. This presentation must be made before commencement of the Work. | 01 35 29
| MSDS |  | Submit to the Contract Administrator one (1) copy of any MSDS as required. These sheets must be submitted before the controlled product is used on Site. | 01 35 29
| Site Plan |  | Submit sit plan showing temporary facilities, utility hookups, staging areas, and parking areas for construction personnel . Submit the Site Plan to the Contract Administrator at least ten (10) Business Days prior to arriving on Site. | 01 50 00
| Fire protection and prevention program |  | Develop and supervise an overall fire-prevention and -protection program for personnel at Project Site. Submit to Contract Administrator. Review needs and establish procedures to be followed. Instruct personnel in methods and procedures. Post warnings and information. | 01 50 00
| Written Request |  | Submit written request to the Contract Administrator in advance of cutting or alteration which affects (existing work). | 01 73 00
| Permits | Electrical | At the time of issuance of any/all electrical Permit(s), provide a copy to the Contract Administrator. | 26 05 01
| Notice | All | The Contractor shall inform the Contract Administrator, in writing, of the attendance at the Site of any Manufacturer's Representative for installation training at least ten (10) Business Days prior to arrival. | 01 65 00
| Documentary Proof | All | Provide documentary proof of the Date of Compliance prior to Substantial Performance listing all equipment and certifying their compliance. Notwithstanding any other remedy available under this agreement or at law for breach of the warranty, any Product that is not Date Compliant shall, within twenty-four (24) hours of receipt of notice of the breach, be repaired or replaced at the Contractor's sole cost and expense, including parts, labour, transportation, and insurance, so as to correct any failure to meet the warranty. | 26 05 01
| As-Built Information Sheets | Instrumentation | Provide data sheets to itemize detailed as-built information regarding the Specification of instruments included as part of this Work for each instrument supplied. The data sheets already included in this Section list specific minimum requirements for particular applications. | 40 70 00
| Form 102 | All | When the Manufacturer’s Representative accepts the installation, they shall certify the installation by completing Form 102 – Certificate of Satisfactory Installation, attached to this Specification. Deliver the completed Form 102 to the Contract Administrator prior to departure of the Manufacturer's Representative from the Site. | 01 65 00
| Manufacturer Field Report | Electrical | Obtain written report from Manufacturer verifying compliance of Work, in handling, installing, applying, protecting, and cleaning of product and submit Manufacturer's Field Reports as described in Section 01 33 00 – Submittal Procedures. | 26 05 01
| Manufacturer Field Report | Electrical | Manufacturer's Field Reports: submit to Contract Administrator Manufacturer's written report, within three (3) Business Days of review, verifying compliance of Work and electrical system and instrumentation testing, as described in Part 3.21 Field Quality Control. | 26 05 01
Pre-Commissioning | Commissioning Plan |  | Contractor is responsible for submitting a detailed Commissioning Plan for the commissioning of the UV systems at least twenty (20) Business Days prior to the planned start of commissioning. The plan shall comply with the requirements that have been established by the Contract Administrator. | 01 91 31
| Test Forms | Instrumentation | Submit test sheet examples e.g. Loop Check Report and Network/Segment Checkout Forms along with proposed Commissioning Plan. | 40 05 00
| Operating and Maintenance Manuals | All | One advance copy of the operating and maintenance manuals shall be submitted to the Contract Administrator for review and comments. After review and acceptance by the Contract Administrator, submit five hard copies and one electronic (PDF) copy of the final operating and maintenance manuals no later than four (4) weeks prior to commissioning of the Work. | 01 91 51
| Notice | All | Inform the Contract Administrator at least fifteen (15) Business Days in advance of conducting the tests and arrange for the attendance of the Manufacturer’s Representative. The tests may be concurrent with the inspection of satisfactory installation if mutually agreed by the Contractor and the Contract Administrator. | 01 91 31
| Notice | Instrumentation | Confirm that all calibrations, required forms and signoffs, and IO and loop checks have been completed prior to providing at minimum two (2) weeks' written notice to the Contract Administrator prior to commissioning for inspection of the following: Proper mounting, Proper connections. | 01 91 31
| Validation Report |  | The validation report shall be submitted to the Contract Administrator at least twenty (20) Business Days prior to starting Commissioning. | 46 66 23
| Commissioning Plan |  | Submit completed Commissioning Plan to the Contract Administrator for review and acceptance. The commissioning plan shall be reviewed prior to its implementation. The Contract Administrator shall be the final arbiter. | 01 91 31
Commissioning and Testing | Notice | All | If the Work is designated for special tests, inspections, or approvals by the Contract Administrator, give notice of a minimum of five (5) Business Days requesting inspection. | 01 45 00
| Test Forms | Instrumentation | Perform tests and record results on test data forms which are included in this Section. Develop additional and/or more detailed test forms as necessary to suit more complex instrumentation. Where the provided test forms are insufficient for the complexity of the test/instrument/equipment, create a similar sheet as required. | 40 05 00
| Printed Record of Serial Numbers | Instrumentation | Prior to calibration, completely program all "smart" transmitters including entries of the appropriate range and tag number. Provide a printed record of smart device serial numbers against their assigned tag number. | 40 05 00
| Tests Performed and Loop Check Results | Instrumentation | Confirm instrument calibrations are complete, PLC or SCADA IO checks are complete, and the scaled ranges for the instruments have been inputted into the PLC/SCADA or signal conditioning equipment prior to loop checks. Each loop check is intended to test the instrument calibration and the scaled value in the controller under real applications to verify the calibrations, instrument settings, loop stability, and readouts. Document the tests performed, and the results of the loop checks for each of the instruments and their values. | 40 05 00
| Notice | Instrumentation | After all devices within a loop have been connected, check the loop for correct functioning and interaction with other loops, where applicable. Provide notice to the Contract Administrator when the loops are going to be tested so that the tests may be witnessed by the Contract Administrator. | 40 05 00
| System Verification Reports | Electrical | Complete all necessary testing, detailed wiring continuity checks, wiring completion checks, installation integrity checks, functional equipment operation checks, and written system verification reports to provide a complete system that is ready for commissioning and start-up. | 26 05 01
| System Verification Report | Instrumentation | Verify instrument calibrations and loop tests and provide a written report. | 40 05 00
| Form 103 | UV Equipment | On successful completion of the demonstration and running test for an individual UV Reactor, Form 103 – Certificate of Equipment Satisfactory Performance (attached to this Specification) will be signed by the Manufacturer’s Representative, the Contractor, and the Contract Administrator. Form 103 is required for each reactor. | 01 91 31
| Running Test Results | UV Equipment | The Contractor shall Submit results of the Running Test to the Contract Administrator within twenty-four (24) hours to the Contract Administrator. Final documented and summarized results shall be submitted in a format acceptable to the Contract Administrator within five (5) Business Days. | 01 91 31
| Form 104 | UV Equipment | On successful completion of the performance test for all reactors, Form 104 – Certificate of Equipment Satisfactory Process Performance (attached to this Specification) will be signed by the Manufacturer’s Representative, the Contractor, and the Contract Administrator. Form 104 is required for each reactor. | 01 91 31
| Performance Test Results | UV Equipment | The Contractor shall submit the results of the Performance Test(s) within twenty-four (24) hours to the Contract Administrator, and final documented and summarized results in a format acceptable to the Contract Administrator within five (5) Business Days. | 01 91 31
| Performance Test Report | UV Equipment | The Manufacturer’s Representative and the Contractor shall provide the Performance Test Report [with details as specified in section 01 91 31] within five (5) Business Days of completion of the test period for each reactor. | 01 91 31
| Certificate of Final Inspection | Instrumentation | Furnish a Certificate of Final Inspection and approvals from Electrical Inspection Department and Supply Authority to the Contract Administrator. | 40 05 00
| Written Certification | Electrical | Upon completion, the Contractor shall certify, in writing, that the required values and settings are complete and that they accurately reflect values required under contract, or the Arc Flash, Short Circuit, and Coordination Study. | 26 05 01
| Validation Report | UV Equipment | Submission of a validation report for the system which has been completed in accordance to the latest version of the United States Environmental Protection Agency (USEPA) UV Disinfection Guidance Manual (UVDGM) considering the polychromatic bias issues (e.g. action spectra correction factor – ASCF). [Report to be composed by De Nora] | 46 66 23
Substantial Performance | Notice | All | Contractor's Inspection: Contractor conduct inspection of the Work, identify deficiencies and defects, and repair as required to conform to Contract Documents. Notify the Contract Administrator in writing of satisfactory completion of the Contractor's Inspection and that corrections have been made. Request the Contract Administrator's Inspection. | SUPPLEMENTALCONDITIONS, D17
| Commissioning Report |  | Contractor to submit the completed Commissioning Report within a maximum of two weeks of completion of the Commissioning. The final Commissioning Report to be reviewed and accepted by the Contract Administrator prior to granting Substantial Performance. | 01 91 31
| Application for Substantial Performance |  | Certificate of Substantial Performance: when the Contract Administrator considers deficiencies and defects have been corrected and it appears requirements of the Contract have been substantially performed, make application for certificate of Substantial Performance. | SUPPLEMENTALCONDITIONS, D17
Training | Training Proposal | Training | Submit training proposal complete with schedule, lesson plan, and name of trainer(s) to the Contract Administrator twenty (20) Business Days prior to anticipated date of beginning of training. | 01 78 24
| Training Materials | Training | Submit Training Materials to the Contract Administrator for review and approval at least three (3) weeks prior to commissioning. | 01 78 24
| Training Video | Training | Submit edited training video within three (3) weeks of final training session | 01 78 24
| Training Documentation | UV Equipment | [Submit] Training documents and training completed [as part of Quality Control submittals in accordance with Section 46 66 23]. | 46 66 23
Total Performance | Quality Control Submittals | UV Equipment | The Contractor shall provide [UV Equipment Quality Control submittals as described in this Section] prior to the issuance of the Certificate of Total Performance. | 46 66 23
| Validation Reports (QC) | UV Equipment | [Submit] UV Equipment Validation reports/certificates [as part of Quality Control submittals in accordance with Section 46 66 23]. | 46 66 23
| Warranties (QC) | UV Equipment | [Submit] Executed warranties [as part of Quality Control submittals in accordance with Section 46 66 23]. | 46 66 23
| Manufacturer Certificate (QC) | UV Equipment | [Submit] Manufacturer’s Certificate of Proper Installation [as part of Quality Control submittals in accordance with Section 46 66 23]. | 46 66 23
| Testing and Start-up Data (QC) | UV Equipment | [Submit] Data summary from testing and start-up period [as part of Quality Control submittals in accordance with Section 46 66 23]. | 46 66 23
| Bill of Materials (QC) | UV Equipment | [Submit] List of all original equipment by model and part number (detailed bill of materials) [as part of Quality Control submittals in accordance with Section 46 66 23]. List manufacturer names, addresses, and phone numbers. | 46 66 23
| PCN (QC) | UV Equipment | [Submit] Updated process control narrative (if modified) and SCADA screens after successful SAT completion [as part of Quality Control submittals in accordance with Section 46 66 23]. | 46 66 23
| Written Certification | All | Completion: Submit written certificate that the following have been performed: Work has been completed and inspected for compliance with the Contract Documents, Defects have been corrected and deficiencies have been completed, Equipment and systems have been tested, adjusted and balanced and are fully operational, Any Certificates required by authorities having jurisdiction have been submitted, Operation of systems have been demonstrated to the City's personnel, Work is complete and ready for final inspection. | SUPPLEMENTALCONDITIONS, D178
| As-Built Drawings | All | On completion of the Work, submit as-built Drawings to the Contract Administrator for review. | 01 78 00
| As-Built Drawings | Instrumentation | Provide as-built Drawings in accordance with Section 01 33 00 – Submittal Procedures and Section 01 78 00 Closeout Submittals. | 40 05 00
Periodical | Updates to Project Schedule |  | Update Project Schedule weekly in advance of Progress Meeting. | 01 32 16
| Safety Meeting Minutes |  | Submit to the Contract Administrator minutes of safety meetings, accident investigations, safety inspections, safety and health program, safety orientation records, hearing test records, copies of safe work procedures and copies of training records. | 01 35 29
| Updates to Schedule of Values and Work Status Report |  | On a monthly basis, include an updated Schedule narrative report identifying Work status to date, comparing current progress to Baseline, presenting current forecasts, defining problem areas, anticipated delays, impact with possible mitigation, and associated updates to completed and upcoming costs. | 01 32 16
| Updates to Commissioning Plan |  | During the construction phase, revise, refine, and update the Commissioning Plan to include approved design and construction changes. Submit each revised Commissioning Plan to the Contract Administrator for review and acceptance. | 01 91 31