## Risk Register
RISK REGISTER
Project: | Lane Closures Application Project
Last Updated: | 2016-10-11
Risk # | Risk Event | Trigger Event | Responsibility | Amount at Stake | Probability | Impact | Response Plan | Priority | Resolution Date | Status | Status Comments
1 | Privacy impact with any potential new information being captured. (e.g. Signage site info, ensuring contractors are aware of how the information is being used) | Office of the Director identifies that the approved improvements in the project requires a privacy impact assessment. | PWD, Records and Information Management Coordinator | Unknown | L | Could delay delivery of the project, waiting on results of privacy impact assessment | PWD, Records and Information Management Coordinator will work together to determine if the changes recommended require a privacy impact assessment | H | - | Existing
2 | Cost (tools, resource changes, etc.) | Project Stage 1 identifies any significant impacts to business processes/resources/system requirements | PWD, Information System and Technology | Unknown | M | Pairing down of requirements | PWD, Information System and Technology will discuss any concerns with the Project Board | HH | - | Existing
3 | System security/availability | Project Stage 1 identifies any significant system requirements that are considered out of the ordinary when it comes to system security/availability | PWD, Information System and Technology | Unknown | M | Delay in delivery of project | PWD, Information System and Technology will discuss any concerns with the Project Board | L | - | Existing
4 | Stage 1 – Resource availability | Christy finds availabilty of resources is insufficient to meet project goals | Business Analyst | Unknown | H | Delay in delivery of project | Business Analyst will discuss any concerns with the Project Board | HH | - | Closed
5 | Any change to business process that would require an update to the "Manual of Temporary Traffic Control on City Streets" | The Traffic Management Branch finds that recommended business process changes will require a revision to the manual | PWD, Transportation Division, Traffic Management | Unknown | HH | Delay in delivery of project (Could take a 4-6 months for City Councel approval, within 6 months most likely) | PWD, Transportation Division, Traffic Management will be involved in any changes to business processes and will identify any changes required to the manual | HH | - | Existing
6 | Mofication of lane closure approvals will cause a change to approval authority | If it is determined that this is a mandatory requirement | Business Analyst | Unknown | L | Heavy impact to business process, resourcing and cost | Identify necessity of requirement | HH | Aug. 29, 2016 | Closed | Discussed with Traffic Management and determined that it is not necessary to give approval authority to Transit, Signals, Parking, Traffic Services.
7 | Lane Closure sources do not comply with manual and does not communicate lane closure/change to lane closure | Resistance with representatives on enforcing TMB notifications of lane closures | Business Analyst | Unknown | HH | Could delay delivery of project and/or affect reliability of lane closure data made available | Get support from the right people | HH | - | Existing
8 | Ongoing translation of Traffic Effect text that is visible to the public is net new effort
9 | Limited access to business internet at construction site for reporting
10 | Unknown who will support requests/incidents concerning LCR/RLC/RR and the application
Note on A6: Risk # Identifier of the risk.
Note on B6: Risk Event: Potential threat or opportunity.
Note on C6: Trigger Event: Event or value which compels contingency implementation.
Note on D6: Responsibility: Person responsible for action.
Note on E6: Amount at Stake: Monetary value of the event's impact.
Note on F6: Probability: Likelihood the risk will become a matter to be addressed. HH - Very High H - High M -Medium L - Low N - No longer probable
Note on G6: Impact: Estimated severity of the event.
Note on H6: Response: Action planned to resolve the risk.
Note on I6: Priority: Degree of importance to affect the project. HH - Very High H - High M -Medium L - Low
Note on J6: Resolution Date: Date by which the risk response will be completed.
Note on K6: Status: Existing or Closed