## RFP
RFP 374-2016 Sample Detailed Breakdown of Fixed Fees Table
Task Description | Role/Project Role: | Total Hours | Total Fees | Type 1 Disbursement | Type 2 Disbursement | Total
Name:
Hourly Rate:
Task 1 : Structural Assessment of the SLA Manhole Opening at Mile 93.69
D7.4.3 (a) Review the relevant reports and reference documents.
D7.4.3 (b) Evaluate the constructability of a larger manhole stack that is either 900mm or 1200mm (preferred) based on whether the SLA can support the larger manhole stack and based on the conditions and location of the site.
D7.4.3 (c) Evaluate previous geotechnical information in proximity to Mile 93.69 to determine if an additional geotechnical investigation is required. For bidding purposes, assume that it is not.
D7.4.3 (d) Develop a concept for a permanent platform and pedestrian walkway for accessing the manhole.
D7.4.3 (e) Investigate if a permanent ladder system for easy access to the SLA from the manhole can be installed.
D7.4.4 (a) Submit a draft and final technical memorandum that summarizes all items in D7.4.
D7.4.5 (a) Schedule and lead a draft review meeting after submission of the draft technical memorandum to discuss the City’s comments.
D7.4.5 (b) A site visit is required to assess the existing conditions of the site.
Task 1 Subtotal
Task 2: Structural Design for Stop Logs Used in the Aqueduct
D7.5.3 (a) Task 2a Complete a structural evaluation of the Mile 42.05 and Mile 83.02 stop logs to determine if they are structurally adequate based on current design codes.
D7.5.3 (b) Task 2b Complete a structural detailed design for the Mile 42.05 and Mile 83.02 stop logs according to current code.
D7.5.3 (c) Task 2c Complete a structural review of the Gore & Storrie design for the stop logs at Mile 17.05, Mile 64.14 and Mile 73.69 to determine if the design is still relevant, if it meets current code and has an appropriate safety factor.
D7.5.3 (d) Task 2d Complete the structural detailed design for new stop logs at Mile 17.05, Mile 64.14 and Mile 73.69 according to current code.
D7.5.4 (a) Submit a final technical memorandum that summarizes the structural evaluation in D7.5.3(a) Task 2a.
D7.5.4 (b) Submit three (3) hard copies and one (1) electronic copy of the structural detailed design and Drawings for the Mile 42.05 and Mile 83.02 stop logs in D7.5.3(b) Task 2b.
D7.5.4 (c) Submit a final technical memorandum that summarizes the structural review of Gore & Storrie’s design in D7.5.3(c) Task 2c.
D7.5.4 (d) Submit three (3) hard copies and one (1) electronic copy of the structural detailed design and Drawings for new stop logs at Mile 17.05, Mile 64.14 and Mile 73.69 in D7.5.3(d) Task 2d.
D7.5.5 (b) A site visit to 552/598 Plinguet Street is required to view and measure the existing Mile 42.05 and Mile 83.02 stop logs.
Task 2 Subtotal
Task 3: Review and Update of the Shoal Lake Aqueduct Emergency Repair Strategy Report (Priority 1)
D7.6.3 (a) Review the SLA Emergency Repair Strategy Report listed in D7.6.2(a).
D7.6.3 (b) Review the SLA Condition Assessment Report listed in D7.6.2(b) for the general condition of the SLA.
D7.6.3 (c) Review Water and Waste’s current standard operating procedures for the water supply system from the Shoal Lake Intake to the Water Treatment Plant (WTP).
D7.6.3 (d) Review the Public Water System Operating Licence number PWS-09-412-01.
D7.6.3 (e) Research, evaluate and recommend current construction equipment and methods for repairs to the SLA and its associated structures.
D7.6.3 (f) Research, evaluate and recommend current materials and technologies for repairs to the SLA and its associated structures.
D7.6.3 (g) Update all sections in the existing SLA Emergency Repair Strategy Report.
D7.6.4 (a) Submit a draft report in Microsoft Word format that summarizes the items in D7.6.3.
D7.6.4 (b) Submit five (5) hard copies and one (1) electronic PDF copy of the final report.
D7.6.5 (a) Schedule and lead a minimum of five (5) progress team meetings to discuss the existing report and to review current SLA operations.
D7.6.5 (b) Schedule and lead a draft review meeting after submission of the draft report to discuss the City’s comments.
D7.6.5 (c) A two day long site tour from the WTP to the Shoal Lake Intake is required.
Task 3 Subtotal
D6.11 Task 4: Pipe Loading Assessment on Branch 1 Aqueduct at the Lafarge Precast Concrete Plant Site:
D7.7.3 (a) Review the Branch 1 Aqueduct design and drawings for the location where the Lafarge Precast Concrete Plant site entrance crosses the Branch 1 Aqueduct.
D7.7.3 (b) Determine the condition of the top of the Branch 1 Aqueduct pipe and nearby joints. (i) Arrange and oversee a Contractor to hydro excavate two (2) locations coinciding with a pipe joint on either side of the Lafarge’s existing driveway that crosses the SLA. The City will pay the contractor directly for their service.
D7.7.3 (c) Complete a topographic survey to confirm the location and extent of the existing Lafarge entrance that crosses the SLA.
D7.7.3 (d) Determine what the SLA’s thermal regime is at the Lafarge Precast Concrete Plant Site.
D7.7.3 (e) Complete a structural analysis of the SLA at the Lafarge Precast Concrete Plant Site to determine the SLA’s load carrying capacity.
D7.7.3 (f) Compare the load carrying capacity of the SLA to the allowable vehicle load capacity of Dawson Road, as designated by the City.
D7.7.3 (g) If the load carrying capacity of the SLA pipe is exceeded by the allowable vehicle load capacity, develop and submit a preliminary concept for an appropriate bridging structure over the SLA at this location. For proposal purposes assume that the load carrying capacity of the SLA pipe is being exceeded.
D7.7.4 (a) Submit a draft and final technical memorandum in Microsoft Word format that summarizes the findings of the visual condition assessment and pipe loading assessment.
D7.7.4 (b) Submit three (3) hard copies and one (1) electronic PDF copy of the final technical memorandum.
D7.7.5 (a) Schedule and lead a draft review meeting after submission of the draft technical memorandum to discuss the City’s comments.
D7.7.5 (b) A site visit is required to determine the condition of the top of the Branch 1 Aqueduct pipe and to complete the topographic survey.
Task 4 Subtotal
D6.12 Task 5: Land Drainage Investigation of Drainage Ditch at Mile 35.38 Drainage Siphon:
D7.8.3 (a) Complete a feasibility analysis on excavating a drainage ditch from the Mile 35.38 siphon to the Brokenhead River.
D7.8.3 (a)(i) Review existing legal plans, drawings and reports of the land drainage in proximity to the Mile 35.38 drainage siphon.
D7.8.3 (a)(ii) Review the required environmental assessments and regulatory approvals that are required for construction.
D7.8.3 (a)(iii) Perform a site investigation.
D7.8.3 (a)(iv) Complete a high level land drainage analysis.
D7.8.3 (a)(v) Assess the constructability of the drainage ditch.
D7.8.3 (a)(vi) Provide recommendations on whether the construction of the drainage ditch is feasible to undertake.
D7.8.3 (a)(vii) Provide recommendations for additional engineering that may be required.
D7.8.3 (a)(viii) Provide an AACE class 3 cost estimate for engineering and construction costs of building the drainage ditch.
D7.8.4 (a) Submit a draft technical memorandum in Microsoft Word format that summarizes the findings of the feasibility analysis.
D7.8.4 (b) Submit three (3) hard copies and one (1) electronic PDF copy of the final technical memorandum.
D7.8.5 (a) Schedule and lead a draft review meeting after submission of the draft technical memorandum to discuss the City’s comments.
D7.8.5 (b) A site visit is required and most likely will have to be undertaken during the winter
Task 5 Subtotal
Task 6: Preparation of Drawings for SLA Crossings Near Plessis Road (Priority 1)
D7.9.3 (a) Review all applicable records, drawings, legal plans and certificates of titles for the oil and gas product pipelines and other utilities crossing the Branch 1 Aqueduct at the following locations: (i) Plessis Road; (ii) Mazenod Road; and (iii) Approximately 500m west of Symington Road.
D7.9.3 (b) Complete a topographic survey of the surface features, including underground utilities that have features that extend to the surface:
D7.9.3 (c) Recommend the vacuum excavation locations that are required to confirm the subsurface utilities location and elevation. For proposal purposes, assume 20 vacuum excavation locations are required. The Department has a standing contract for vacuum excavation services and will arrange for these services.
D7.9.3 (d) Develop a composite site plan drawing for each location listed in D7.9.3(a). Refer to the PDF titled “Example Site Plans” for examples that show the required level of detail.
D7.9.3 (e) Develop detailed profile drawings to show all utilities that cross over or under the Branch 1 Aqueduct for each location listed in D7.9.3(a)
D7.9.4 (a) Submit five (5) A1 hard copies, one (1) PDF, and one (1) AutoCAD file of the draft and final composite site plans.
D7.9.4 (b) Submit five (5) A1 hard copies, one (1) PDF, and one (1) AutoCAD file of the draft and final detailed profile Drawings.
D7.9.5 (a) Schedule and lead one (1) progress team meeting.
D7.9.5 (b) Site visits are required for the survey/vacuum excavations at each location listed in D7.9.3(a)
Task 6 Subtotal
Task 7: Detailed Condition Assessment of Shoal Lake Aqueduct Boathouses and associated overflow structures:
D7.10.3 (a) Review technical reports, drawings and photographs regarding the design, construction and upgrades to the thirteen (13) boathouses and five (5) overflow structures.
D7.10.3 (b) develop an inspection protocol for the inspection of the boathouses, overflow chambers, energy dissipation chambers and outlet structures. At a minimum, the inspection protocol shall include:
D7.10.3 (b)(i) a safe work plan for the inspection.
D7.10.3 (b)(ii) an inspection spreadsheet that lists the boathouses, overflow chambers, energy dissipation chambers and outlet structures and their respective components that are to be inspected.
D7.10.3 (b)(iii) A schedule for the inspection activities. Coordinate the inspections with the Project Manager.
D7.10.3 (c) Complete a detailed inspection on the thirteen (13) boathouses and five (5) overflow structures based on the approved inspection protocol. The boathouses are in remote locations and access to some sites will need to be made through the GWWD Railway
D7.10.4 (a) Submit the safe work plan, inspection spreadsheet and inspection schedule for the City to review at least two (2) weeks prior to the start of the inspection.
D7.10.4 (b) Submit a draft and final inspection report that summarizes the findings of the boathouse and overflow structure inspections.
D7.10.5 (a) Schedule and chair a meeting with City staff to present and discuss the inspection protocol at least (2) weeks prior to the start of the inspection.
D7.10.5(b) Schedule and lead a draft review meeting after submission of the draft report to discuss the City’s comments.
D7.10.5 (c) Site visits are required for the detailed inspections. For proposal purposes allow one (1) eight (8) hour day for each boathouse location.
D7.10.5 (d) A site visit to one (1) boathouse in the winter is required.
Task 7 Subtotal
Task 8: Preliminary Design of Boathouse Superstructures and Energy Dissipation Chamber / Outfall at Mile 64.14:
GENERAL: D7.11.3 (a)(i) Preliminary design shall be completed on the thirteen (13) boathouses and five (5) overflow structures for the locations listed in D7.10.3(a). For proposal purposes, it is assumed that 6 boathouse superstructures require replacement, 7 boathouse superstructures require rehabilitation and only the Mile 42.05 energy dissipation chamber and Mile 42.05 outlet structure requires rehabilitation as specified in the spreadsheet in the Task 7 & 8 – “Boathouses” on the City's FTP site.
D7.11.3 (a)(ii) Complete a life cycle cost analysis to determine which boathouses and overflow structures should be rehabilitated and which should be replaced.
GEOTECHNICAL: D7.11.3 (b)(i) Assess and recommend the level of geotechnical soil testing that will be required to obtain appropriate Waterways construction permits as well as any other required construction permits.
D7.11.3 (b)(ii) Assess and recommend the type and number of geotechnical investigations that will be required for future detailed design.
D7.11.3 (b)(iii) Complete a geotechnical investigation to determine the geotechnical stability of the overflow structure at Mile 64.14. The Consultant is responsible for engaging a drilling Subcontractor for the required work. The City will pay the Contractor directly for their work. • Drill at least two (2) test holes to below foundation depths. • Classify and test the soils. • Install and monitor a slope inclinometer. For proposal purposes assume that one (1) slope inclinometer is required and monthly monitoring is required for the first year and quarterly monitoring is required for the second year. • Install and monitor static piezometers to establish groundwater levels. For proposal purposes assume that two (2) piezometers are required and monthly monitoring is required for the first year and quarterly monitoring is required for the second year. • Survey the locations of the test holes, the slope inclinometer and the static piezometers to tie-into the existing boathouse superstructure.
STRUCTURAL: D7.11.3 (c)(i) Determine if the Aqueduct can accommodate the new boathouse superstructures. Incorporate the existing overhead beam in the new boathouse design.
D7.11.3 (c)(ii) investigate various structural replacement options for the boathouses that are to be replaced and recommend the best option.
D7.11.3 (c)(iii) Investigate coatings and liners for the interior of the boathouses to reduce concrete deterioration from freeze/thaw attack and provide a recommendation for the best coating or liner.
D7.11.3 (c)(iv) investigate environmentally suitable door alternatives for the boathouses.
D7.11.3 (c)(v) Assess if a permanent bracket for a personnel safety hoist can be installed in the floor of all boathouses.
MECHANICAL: D7.11.3 (d)(i) Investigate various ventilation and insulation replacement options to prevent frost build up within the boathouses and provide a recommendation for the best option
ELECTRICAL: D7.11.3 (e)(i) develop a detailed plan for a temporary support (if required) and protection for the electrical and flow monitoring panels during the restoration of the boathouses.
D7.11.3 (v) Additional Items which relate to the Design of the boathouses.
D7.11.3 (f)(i) Preliminary design for a new six (6) meter wide all weather access road from Mile 82.44 to the boathouse at Mile 83.02. The Department will negotiate the relocation of the existing powerline with MB Hydro.
• Review existing drawings and photographs.
• Complete a site investigation and survey of the immediate area surrounding the SLA from Mile 82.44 to (and including) the boathouse at Mile 83.02.
• Complete the preliminary design of the six (6) meter wide all weather access road from Mile 82.44 to the boathouse at Mile 83.02.
• Complete the preliminary design of a turnaround for vehicles in proximity of the Mile 83.02 boathouse.
• Complete a land drainage assessment on the drainage between the proposed road and the Aqueduct.
• Complete the preliminary design of a robust vehicular security gate on the north side of the Aqueduct at Mile 82.44.
• Complete the preliminary design for an Aqueduct bridging structure at Mile 82.44, such as a timber mat bridge, a truss panel bridge, or some other bridge configuration that carries the vehicle and equipment loads over the SLA. Include: - Review the existing drawings and photographs. - Complete a visual inspection of the inside of the SLA at Mile 82.44 during the annual fall Aqueduct shutdown. - Determine what the SLA’s thermal regime is at Mile 82.44. - Complete a structural analysis of the SLA pipe at Mile 82.44 to determine its load carrying capacity. - Compare the load carrying capacity of the SLA pipe to the allowable vehicle load capacity of the existing public road, as designated by MI. - If the load carrying capacity of the SLA pipe is exceeded by the allowable vehicle load capacity, develop and submit a preliminary concept for an appropriate bridging structure over the SLA at this location. For proposal purposes assume that the load carrying capacity of the SLA pipe is being exceeded.
D7.11.3 (f)(ii) Preliminary flood proof plan for the boathouse at Mile 83.02
• Review existing drawings of the boathouse and the documents regarding past flooding events at the Mile 83.02 boathouse.
• Complete a site investigation of the drainage surrounding the Mile 83.02 boathouse.
• Complete a land drainage assessment on the area surrounding Mile 83.02.
• Complete a preliminary flood proofing plan such that enhancing the drainage in the area may not be required. The plan should layout the required steps that need to be taken by City staff during periods of high water.
D7.11.3 (f)(iii) Complete a feasibility analysis of installing new inclined bar screens at Mile 17.05 and Mile 96.77.
• Review photographs and documents pertaining to the existing bar screens at Mile 17.05 and Mile 96.77.
• Review the “Culvert and Drainage Inlet/Outlet Safety Guidelines” report by UMA Engineering Ltd.
• Complete a feasibility analysis of installing inclined bar screens in the SLA at Mile 17.05 and Mile 96.77. Consider modular configuration for easy installation and removal.
D7.11.3 (g)(i) Complete AACE Class 3 cost estimates for the following: • Detailed design, construction and contract administration for rehabilitation/replacement of the thirteen (13) boathouses and five (5) overflow structures at the locations listed in D7.10.3(a). • Detailed design, construction and contract administration for the new six (6) meter wide all weather access road from Mile 82.44 to Mile 83.02. • Costs of materials required for flood proofing at Mile 83.02. • Detailed design, construction and contract administration for installation of new bar screens at Mile 17.05 and Mile 96.77.
D7.11.4 (a) Submit seven (7) hard copies and one (1) electronic Microsoft Word copy of the draft preliminary design report for all items in D7.11.3(a) to D7.11.3(g).
D7.11.4 (b) Submit seven (7) hard copies and one (1) PDF of the final preliminary design report and drawings for all items in D7.11.3(a) to D7.11.3(g).
D7.11.5 (a) Schedule and lead at least four (4) progress team meetings.
D7.11.5 (b) Schedule and lead a draft review meeting after submission of the draft preliminary design report to discuss the City’s comments.
D7.11.5 (c) A site visit during the annual SLA fall shutdown is required to view the existing bar screens and the inside of the SLA at Mile 17.05, Mile 82.44 and Mile 96.77.
D7.11.5 (d) A site visit/survey is required for the immediate area surrounding the SLA from Mile 82.44 to the boathouse at Mile 83.02.
Task 8 Subtotal
Task 9: Condition Assessment on Shoal Lake Aqueduct Underdrain Outfalls to Water Courses:
D7.12.3 (a) Review the drawings regarding the SLA underdrain outfalls at the following locations: (i) Plinguet Street / Mctavish Street intersection to the Seine River. (ii) Notre Dame Street / Maisonneuve Street intersection to the Seine River. (iii) Tache Avenue / Messager Street intersection to the Red River.
D7.12.3 (b) Complete a condition assessment during periods of low river levels on each underdrain outfall listed in D7.12.3(a).
D7.12.3 (b)(i) Determine if the underdrain outfall is functional and drains water away from the SLA.
D7.12.3 (b)(ii) Determine the horizontal and vertical position of the underdrain outfall using GPS. The results shall be compared to previous record information or coordinates where they exist. Submit GIS error reports to the Project Manager.
D7.12.3 (b)(iii) Identify flow restrictions including roots, encrustations, sediment buildup and vegetative growth inside the pipe and around the underdrain outfall.
D7.12.3 (b)(iv) Evaluate the structural integrity of the underdrain outfall including cracking, deformation, ice damage, seepage, and concrete deterioration.
D7.12.3 (b)(v) Determine if there is any loss of soil around the underdrain outfall and voids or cavities outside the underdrain outfall.
D7.12.3 (b)(vi) Document the condition of the underdrain outfall using photographs.
D7.12.3 (b)(vii) During high water elevations in the water course determine if water is backing up or has the ability to backup into the underdrain.
D7.12.3 (b)(viii) If water has the ability to backup into the underdrain, determine the amount of time that it will be surcharged and the distance that the water will flow back into the underdrain.
D7.12.3 (b)(ix) Determine what happens to the flow in the underdrain outfall during the winter.
D7.12.3 (b)(x) Determine if there are opportunities for the underdrain to be cross connected to a nearby LDS in order to eliminate the need for a separate underdrain outfall into the water course. • Determine if the nearby LDS has backflow prevention in the form of a positive gate and a flap gate. • Determine if the nearby LDS is part of a system that has permanent flood pumps or can accommodate temporary flood pumps. • Perform a preliminary geotechnical investigation to determine if the nearby LDS outfall is in a riverbank that is stable. A geotechnical investigation program shall be proposed and included in the Fee Proposal.
D7.12.3 (b)(xi) Recommend whether additional work, such as geotechnical assessments or cleaning and televising etc. is required.
D7.12.4(a) Submit a draft and final technical memorandum that summarizes all items in D7.12.
D7.12.5 (a) Schedule and lead at least two (2) progress team meetings.
D7.12.5 (b) Schedule and lead a draft review meeting after submission of the draft technical memorandum to discuss the City’s comments.
D7.12.5 (c) A site visit is required to inspect the three (3) underdrain outfalls listed in D7.12.3(a).
Task 9 Subtotal
D6.16 Task 10: Preliminary Engineering for Splitting of the Deacon Booster Pumping Station Suction Header:
D7.13.3 (a) Review all relevant drawings and information.
D7.13.3 (b) Become familiar with the water system operation from the WTP to the in-town reservoirs and pumping stations.
D7.13.3 (c) Develop feasible concepts for splitting the DBPS suction header. All concepts shall include a valve incorporated into the divider wall.
D7.13.3 (d) Identify and develop the logistics for getting the divider wall components into the suction header and the assembly of the divider wall complete with the valve for each feasible concept.
D7.13.3 (e) Identify and develop the operational sequencing for each feasible concept.
D7.13.3 (f) Recommend a preferred concept.
D7.13.3 (g) Develop a preliminary implementation plan for the preferred concept.
D7.13.3 (h) Complete a risk assessment for each step in the implementation plan.
D7.13.3 (i) Consult with the regulator to determine if there are any regulatory issues with the preferred concept.
D7.13.3 (j) Complete an AACE Class 3 cost estimate for the detailed design and construction of the splitting of the DBPS suction header.
D7.13.4 (a) Complete a draft and final technical memorandum that summarizes all items in D7.13.3.
D7.13.4 (a) Schedule and lead the following meetings throughout this task:
D7.13.5 (a)(i) A familiarization meeting with Water Services Operations staff to identify operational opportunities to undertake this work.
D7.13.5 (a)(ii) A review meeting to present the feasible concepts to the City’s project team and to determine the preferred concept.
D7.13.5 (a)(iii) A minimum of two (2) progress team meetings.
D7.13.5 (a)(iv) A draft review meeting after submission of the draft technical memorandum to review all City comments.
D7.13.5 (b) A site visit is required at the DBPS to view the existing facility.
Task 10 Subtotal
D6.13 Task 11: Land Drainage Improvements at Mile 77.6 Railway Yard:
D7.14.3 (a) Preliminary Design
D7.14.3 (a)(i) Perform a land drainage site investigation, including a topographic survey of the land immediately surrounding the culvert.
D7.14.3 (a)(ii) Complete a land drainage analysis of the drainage in the area immediately surrounding the culvert to determine the appropriate size and type of hydraulic conveyance system.
D7.14.3 (a)(iii) Perform a geotechnical investigation sufficient to design the recommended land drainage conveyance system. A geotechnical investigation program shall be proposed and included in the Fee Proposal.
D7.14.3 (a)(iv) Prepare an AACE Class 3 cost estimate for construction and contract administration.
D7.14.3 (b) Detailed Design
D7.14.3 (b)(i) Complete the detailed design for the construction of a new culvert or a surface drainage channel at Mile 77.6 and for the removal/abandonment of the existing culvert.
D7.14.3 (b)(ii) Identify and obtain the required regulatory approvals for the work, including approvals from: • Manitoba Conservation; • Department of Fisheries & Oceans; • Navigable Waters Protection Program; and • Any other required regulatory approvals.
D7.14.3 (b)(iii) Interface with the Rural Municipality of Reynolds and MI regarding the design and construction of the new culvert or surface drainage channel at Mile 77.6.
D7.14.3 (b)(iv) Prepare a draft and final Bid Opportunity for the construction of the new culvert or surface drainage channel at Mile 77.6.
D7.14.3 (c) Non-Resident Services
D7.14.3 (c)(i) Administer the construction contract.
D7.14.3 (c)(ii) Conduct a pre-construction meeting.
D7.14.3 (c)(iii) Review and provide recommendations for requests for alternate materials and methods. No alternates shall be approved without written authorization from the City.
D7.14.3 (c)(iv) Coordinate regular construction meetings and provide minutes. The meetings shall include representatives from the City and the Contractor.
D7.14.3 (c)(v) Prepare, certify and submit progress estimates to the City for payment to the Contractor.
D7.14.3 (d) Resident Services
D7.14.3 (d)(i) Provide full time inspection services when the Contractor is on-site to ensure that construction conforms to the design drawings and specifications.
D7.14.3 (d)(ii) Perform a final inspection of the project with the Contractor and the City prior to substantial performance and prior to Total Performance. Provide written appropriate recommendation of acceptance of the constructed or partially constructed project.
D7.14.3 (d)(iii) Perform a warranty inspection of the Project with the Contractor and the City prior to issuance of the Certificate of Acceptance.
D7.14.3 (d)(iv) Prepare draft and final as-built Drawings.
D7.14.4 (a) Submit a draft and final technical memorandum that summarizes all items in D7.14.3(a) Preliminary Design.
D7.14.4 (b) Submit draft and final copies of the Bid Opportunity package. (i) Include five (5) 11x17 hard copies and one (1) electronic copy.
D7.14.4 (c) Submit draft as-built Drawings within one month of Total Performance for City review. (i) Include five (5) 11x17 hard copies and one (1) electronic copy.
D7.14.4 (d) Submit one (1) set of size A1 Mylar, and one (1) electronic copy of PDF and AutoCAD files of the final as-built Drawings.
D7.14.5 (a) Schedule and lead a draft review meeting after submission of the draft technical memorandum to discuss the City’s comments.
D7.14.5 (b) A site visit is required to perform the land drainage site investigation and survey.
D7.14.5 (c) Full time resident inspection services are required.
Task 11 Subtotal
Task 12: Topographic Surveys and Preparation of Drawings:
D7.15.3 (a) Review all applicable records, drawings, legal plans and certificates of titles for the following locations: (i) Ross Railway Yard (Mile 39); (ii) Hadashville Railway Yard (Mile 64); (iii) East Braintree Railway Yard (Mile 77); (iv) Mile 41.3 Area; (v) Cooks Creek Site Drawing at Mile 22.15;
D7.15.3 (b) Survey surface features, including those that are appurtenances of existing subsurface utilities and services for each location listed in D7.15.3(a).
D7.15.3 (c) Develop a comprehensive site plan drawing for each location listed in D7.15.3(a). Refer to the PDF titled “Example Site Plans” for examples that show the required level of detail.
D7.15.3 (d) Create a new SLA cross section drawing similar to drawing D-5782 that includes all 31 SLA cross sections from the Shoal Lake Intake to the McPhillips Pumping Station.
D7.15.4 (a) Submit five (5) A1 hard copies, one (1) PDF and one AutoCAD file of the draft and final composite site plans for each location listed in D7.15.3(a).
D7.15.4 (b) Submit five (5) A1 hard copies, one (1) PDF and one AutoCAD file of the draft and final SLA cross section drawing listed in D7.15.3(d).
D7.15.5 (a) Schedule and lead at least one (1) progress team meeting.
D7.15.5 (b) Site visits are required for the survey at each location listed in D7.15.3(a).
Task 12 Subtotal
Task 13: Shoal Lake Aqueduct Preliminary Plan for the Crossing at Provincial Road No. 308:
D7.16.4 (a) Review all applicable records and drawings of the SLA at Mile 77.71.
D7.16.4 (b) Review the Letter Report by UMA Engineering Ltd. regarding the 2003 SLA Rehabilitation Program - PR No. 308 - Aqueduct Crossing at Mile 77.71.
D7.16.4 (c) Review the 1998 “Shoal Lake Aqueduct Rehabilitation: PR No. 308 Bridging Structure Geotechnical Report” by UMA Engineering Ltd.
D7.16.4 (d) Conduct a site visit to examine the condition of the existing crossing at Mile 77.71.
D7.16.4 (e) Perform a survey to reconcile the road cover over the SLA, the road profile crossing the SLA and the railway profile from the bridge location to 500m east of PR. No. 308.
D7.16.4 (f) Complete a visual inspection on the inside of the SLA at Mile 77.71 during the annual fall Aqueduct shutdown.
D7.16.4 (g) Determine what the thermal regime is at this location due to the SLA berm having been cut down to accommodate PR No. 308.
D7.16.4 (h) Undertake a structural analysis of the SLA pipe to determine its load carrying capacity.
D7.16.4 (i) Compare the load carrying capacity of the SLA pipe to the allowable vehicle load capacity of PR No. 308, as designated by MI.
D7.16.4 (j) If the load carrying capacity of the SLA pipe is exceeded by the allowable vehicle load capacity, develop and submit a preliminary concept for an appropriate bridging structure over the SLA at this location. For proposal purposes assume that the load carrying capacity of the SLA pipe is being exceeded.
D7.16.5 (a) Submit a draft and final technical memorandum that summarizes at items in D7.16.4.
D7.16.6 (a) Schedule and lead a draft review meeting after submission of the draft technical memorandum to discuss the City’s comments.
D7.16.6 (b) After acceptance of the final technical memorandum, attend and participate in a meeting with MI to discuss the preliminary bridging structure concept. (i) Prepare meeting minutes for this meeting.
D7.16.6 (c) One (1) site visit is required to complete the site inspection and survey.
D7.16.6 (d) One (1) site visit is required to inspect the inside of the SLA at Mile 77.71 during the annual fall Aqueduct shutdown.
Task 13 Subtotal
Project Management - Including monthly project status reports
Total Hours
GRAND TOTAL