## Template Instructions
Business Case (BC) Template Instructions
This template identifies the key elements contained in the Business Case and aligns with the Investment Planning Process. The objective is to ensure each Business Case (BC) is completed in a consistent manner. The intended result is that all stakeholders will know what to expect when they ask for the BC Template. Only enter information in the white cells - do not overwrite any wording or formulas in greyed out cells.
There are nine parts to the BC Template: 1) Tab 2 - Needs Assesment This tab identifies the Need for the Investment: the Gap in Level of Service, the Root Cause, Consequences, and Risk to Level of Service
2) Tab 3 - Options Analysis Divided into sections based on the life cycle of the Business Case (Feasibility Study / Preliminary Design Study phases). The user needs to outline what options have been identified, the costs associated with each option, and the pros vs cons of considering each option. Solution needs to be outlined and rationale given.
3) Tab 4 - Investment Summary This worksheet identifies the ask for budget submission. The information in this tab is also aligned to the Capital Budget Detail Sheet submission template. This tab includes information that is summarized at the bottom that can be copied and pasted into the MCP tool.
4) Tab 5 - Basis of Estimate: Summary This section identifies information that supports the financial dollars in the BoE Cost Detail.
5) Tab 6 - Basis of Estimate: Cost Detail This section itemizes costs to perform all activities to deliver the investment. These costs are then spread out over the length of the project in order to apply inflationary interest costs. ** It is important that specific cost groups or items are not deleted if the items are not applicable; leave blank or add N/A.
6) Tab 7 - Class of Estimate This sheet helps the BoE author rationalize the Class of Estimate by identifying key elements that define a specific Class of Estimate per AACE.
7) Tab 8 - Basis of Estimate: Rationale This sheet provides the BoE author a workspace to identify how costs or class estimates were derived.
8) Appendix The purpose of this section is to capture any supplementary information that supports the BC (charts, maps, photos, etc.)
9) Approval & Change log This sheet documents who has signed off on the BC and any changes made to the versions.
Follow the instructions below for each of the Needs Identified field descriptions to complete the BC Template.
Tab 2 - Needs Assessment
Level of Service (LOS) Gap | Current LOS should be stated with the Desired / Target LOS. Define the Target Service Level in terms of a customer and/or the asset performance measures and identify the gap in that service (performance). Use Key Performance Indicators (KPIs) if possible.
Root Cause | Explore the underlying reasons why the need exists (be succinct, avoid duplication/redundancy, highlight key items in bullet form). Ask yourself the question “why” 5 times and you should arrive at the root cause of the need (problem) to be addressed. This is important as it will focus on the problem that your solution addresses. This will be a key focus at the Challenge session.
Risk to Level of Service (LOS) | What is the negative impact to service level and the customer if this investment does not proceed? Describe the risk in terms of Consequences and Likelihood. This should align with outputs from the Asset Risk Model (some Departments have, future Corporate Initiative).
Internal Stakeholders consulted in the development of the BC | The intent is to identify the individuals or groups consulted with during the development of the Business Case.
Evidence and Data | List the specific documents that were used to provide the information in the above sections. Key pieces of documentation could be included in the Appendix or reference links to documents.
Tab 3 - Options Analysis
The intent of this section is to identify options that are viable solutions to address the problem or need. Not all BC will have options but the Author will need to justify why there is only a single option to address the problem identified in the root cause section above. This justification will be a focus at the Challenge session.
Need Validated and Next Steps Phase
Action to address the Need identified? | Detail what you need to do in order to address the need. This sets you up for a Feasibility Study. A Feasibility Study can be conducted by an external source, or the act of performing Option Analysis internally. If the Feasibility Study is done externally, this step requires budget approval and the "ask" will be the funding required to hire a consultant to identify options. Proceed to Tab 4 Investment Summary to request budget approval.
Project Management Supporting documents | This section is to identify and link to completed PM supporting documents. Examples include: - Whole Life Cost Analysis (NPV results) - Project Charter - Project Delivery Plan - Project Risk Assessment (use the Risk Management Plan template) - Schedule - Stakeholder Assessment & Communication Plan - Feasibility Study (if conducted by consultant), other Some documents will be revised as the project progresses. Proper version control of PM documents will ensure the BC reviewer can identify the correct document.
Project Deliverables Feasibility Study
Options Analysis
Feasibility Study Check box | Select (check) once this step is complete.
Option (1-3) Description: | For each Option, briefly describe the option (same description used in the NPV).
Option (1-3) Cost: | For each Option, state the cost estimate of the Option.
Option (1-3) Cost/Benefit Score: | For each Option, state the cost/benefit score from the NPV template.
Option (1-3) Pros & Cons | Briefly describe in bullets the benefits and drawbacks to each Option.
Option Recommended and Rationale
Clearly state which Option you are recommending and why this option is preferred. Talk to the items identified in the Pros & Cons section above. If only a single option, justify why only one option was considered and is viable.
Measureable Benefits of Preferred Solution
Quantified Benefits – Specify the benefits that the Customer will realize from this project. This translates the “need” into terminology that states what will be achieved in those same measures by completing this project. These benefits will be tracked in Project Delivery and/or by Operations to assess the success of making this investment.
Project Deliverables Preliminary Design Study
Outline details of the Project that align with the Class 3 estimate. If the Preliminary Design Study is to be done externally, this step requires budget approval and the "ask" will be the funding required to hire a consultant to identify options. Proceed to Tab 4 Investment Summary to request budget approval.
Refining Selected option to Class 3 | This starts the Preliminary Design phase in the Business Case life cycle, check box when complete.
Tab 4 - Investment Summary
This section provides information and details for the Capital Budget ask, and starts to form the basis of a project. Outline the scope and funding needed. The Summary can be copied and pasted into the Multi-Criteria Prioritization (MCP) tool for Investment Planning.
Investment Summary
Investment Title | This should be relevant to the project you are proposing
Business Case ID | Format:
o BC_department_business unit_year_sequential# (eg BC_WWD_AM_2014_0014)
The sequential number should be obtained from your Departmental Representative / AMO
Class of Estimate | This cell will auto-populate from the BOE Class Estimate tab
Project/Program ID | PeopleSoft ID assigned and included on detail sheets (leave blank for new projects/programs)
Department | Select from dropdown list
Dept ID | Select from dropdown list
Division / Branch | Spell out, no abbreviations
Date | Date Investment Summary page created
Business Case Author | Project Manager or individual responsible for the BC content
Scope Statement
This is a brief, plain-language explanation of the project proposed. This may be copied into the Capital Budget Detail Sheet template Include project description, timeframe, justification, estimated asset life.
Significant Dependencies / Synergies
This refers to other capital projects with SIGNIFICANT synergies/dependencies; i.e. the proposed project couldn’t proceed without Project B; or there are significant cost savings by delivering projects together. This area only needs to be completed if applicable as most projects do not have significant dependencies with other projects or events.
Project Driver (% allocation) | What gap in service level is driving the need for this project (to the nearest 10%)? o Maintain Existing LOS - The capital investment required to maintain existing levels of service to existing customers. This includes replacement of aging assets with the modern equivalent to meet current code. o Enhanced LOS - The capital investment required to deliver enhanced levels of service. o Regulatory - The capital investment required to meet new legislative requirements. Meeting an existing legislative or regulatory requirement is Base Maintenance. o Growth - The capital investment required to deliver existing levels of service to future increases in customers. This includes increases in service demand due to factors other than population growth. As a general guide, Maintain Existing LOS tends to be opex neutral (i.e. no impact to the Operating Budget) while Regulatory/Enhanced LOS/Growth tend to lead to increases in opex.
Latitude / Longitude | To align with future Capital Dashboard implementation. If known, input the coordinates for the approximate project location. **Capital Dashboard PM will provide a process and tool for capturing the coordinates for use**
Authorized Previous Budget to Date | For multi-year projects, sum of previous years’ capital budget approvals (NOT cash spent to date). For Programs, put in the word “annual”.
Rebudget Summary | Amount of previously approved budget being cancelled and rebudgeted.
Total Project Capital Cost | Complete capital cost of Project; for most projects will be the sum of Authorized Previous Budget to Date and the 1+5 year Capital Budget ask.
Type | Select from dropdown list.
Funding Sources | Select from dropdown list; if multiple sources, select 'other'; if unknown, leave blank.
If Program, # projects in budget year | Approximate number of projects to be completed within the program in the budget year.
Capital Budget Authorization
Capex | Enter requested capital budget funds in appropriate year.
Net Opex, Escalation, Contingency | These cells will auto-populate from the BOE Cost Detail tab.
Service View Budget Category | Select from dropdown - from capital budget detail sheet or Service View category table.
OurWinnipeg Reference(s) | Identify what strategic goal or objective for “OurWinnipeg” the BC is addressing.
Department Strategic Plan(s) Considered | Identify any Strategic plan(s) that the BC is addressing, if applicable. This could include a Corporate Strategic plan as well.
Benefit Analysis
Refer to the MCP scoring guidelines to populate these cells. http://citynet/finance/infrastructure/camp/#5
Summary
This summary autopopulates from cells throughout the worksheet. For informational purpose only: the format is identical to the MCP tool and allows the user to copy and paste the cells into the MCP. All cells are populated except the Project # (to be determined while using the MCP tool) and the Grants and other external fundings cell (needs to be entered at the MCP analysis stage to preserve the formula in the cell). ***Your Departmental Investment Planning lead will copy and paste these cells into the MCP tool***
Tab 5-8 - Basis of Estimate Related Tabs
These tabs relate to the Basis of Estimate (BoE) for the project. For the time being, instructions on filling out the BoE can be found on the separate BoE template on the Corporate Finance Intranet under Investment Planning: http://citynet/finance/infrastructure/camp.stm#4 or speak to your Branch/Division lead.

## Tab5-BOE Summary
Business Case ID:
Investment Title:
Date:
BoE Author:
BoE Reviewer:
4. Basis of Estimate: Summary
Key Scope Elements or Requirements:
Out of Scope:
Assumptions/Sensitivities:
Risks and Opportunities:
Estimating Team:
Reference Documents (For Estimate Development):
Major Changes from Previous Estimate:
General Comments:

## Tab6-BOE Cost Detail
0
5. Basis of Estimate: Cost Detail
SECTION A: CAPITAL CASH FLOW
Cost Escalation / Construction Inflation
| ($ thousands) |  | Estimate Year | Year Project/Work Undertaken | [7 empty] | % of Project Work Undertaken | [5 empty] | Check
| Estimate Detail | % of Const. | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Total |  | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Total %
Construction Costs
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering Costs |  | % of Const
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction & Engineering Sub-total |  | 0
Utility Costs |  | % C&E
| Hydro | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Communication - MTS | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Communication - Shaw | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Costs |  | % C&E
| IST | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Internal | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Costs before Contingencies Sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingencies Costs |  | % Proj Cost
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | % Proj Cost | [6 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
% increase from base
| Project Sub-total before Charges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Administrative Overhead Charges
| Total Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3rd Party Share of Project Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| City's Share of Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Departmental |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Corporate Admin (max $100,000) | 1.25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research (SMIR) (Const only) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MRST | 8% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overhead & Admin Charges Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Financing Charges
| Corporate Interest | 2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
SECTION B: OPERATING
Operating Budget Impact Detail
|  |  | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Salaries and Benefits
Materials, Parts and Supplies
Other
| Net Operating Impact |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash flow extends beyond 6-year window
Note on E5: Amann, Ron: Indicate the Escalation % per year starting from the Estimate Year. Typically, it is the same for each but can change based on the investment. The Escalation Rate in future years will be reflected in the costs of each line item based on the year that the work occurs.
Note on D6: Molinski, Krista: Year in which costs are based.
Note on E7: Amann, Ron: Enter the year that the work will occur. The years do not need to be sequential. That is, work does not need to start the first year after the Estimate Year and work does not have to occur for 1 or more years.

## Tab7-Class of Estimate
0
6. Class of Estimate
Overall Class of Estimate:
Table 1 - Classification of Estimate Analysis | [8 empty] | Legend
| Characteristic | Weighting | Class 1 | Class 2 | Class 3 | Class 4 | Class 5 | Comments |  | BoE Author's Determination (highlighted selection)
1 | Project Definition | Primary | 65% to 100% | 30% to 75% | 10% to 40% | 1% to 15% | 0% to 2% |  | Blank | Development of the deliverable has not begun.
2 | End Usage | Secondary | Tender Check | Semi-Tender | Budget | Study | Screening |  | S | Rough work on the deliverable has begun.
3 | Methodology | Secondary | Detailed Unit Cost with Detailed Take-off Cost | Detailed Unit Costs with Forced Detailed Take-off Cost | Semi-detailed Unit Cost with Assembly Level Line Items | Parametric Models, Assembly-Driven Models | SF (sq.ft.) Factoring, Parametric Modeling, Judgment, Analogy |  | P | Work on the deliverable is advanced and may be complete, excepting final review and approvals.
4 | Expected Accuracy (from Appendix 2 - Cap Bug) | Secondary | High: +3% to +10% Low: -3% to -5% | High: +10% to +20% Low: -5% to -10% | High: +20% to +30% Low: -10% to -20% | High: +30% to +60% Low: -20% to -30% | High: +60% to +100% Low: -30% to -50% |  | C | Deliverable has been reviewed and approved as appropriate.
[9 empty] | n/a | Not applicable. The criteria does not apply to the project.
Table 2 - Supporting Class of Estimate Rationale
General Project Data
1 | General Scope Description |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
2 | Project Location |  | Specific | Specific | Specific | Approximate | General | n/a
3 | Functional Space Req (m2) |  | Specific | Specific | Defined | Preliminary | Started | n/a
4 | Standards Requirements |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
5 | Total Capacity |  | Defined | Defined | Defined | Defined | Preliminary | n/a
6 | Electrical Capacity |  | Defined | Defined | Defined | Defined | Preliminary | n/a
7 | Soils / Hydrology Report |  | Defined | Defined | Defined | Preliminary | None | n/a
8 | Integrated Project Plan |  | Defined | Defined | Defined | Preliminary | None | n/a
9 | Project Master Schedule |  | Defined | Defined | Defined | Defined | Approximate | n/a
10 | Work Breakdown Structure |  | Defined | Defined | Defined | Defined | Preliminary | n/a
11 | Project Code of Accounts |  | Defined | Defined | Defined | Defined | Preliminary | n/a
12 | Contracting Strategy |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
13 | Escalation Strategy / Basis |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
Design Deliverables
14 | Standards Drawings |  | C | C | C | S/P |  | n/a
15 | Site Plan |  | C | C | C | S/P | S | n/a
16 | Existing Site Plan |  | C | C | C | S/P | S | n/a
21 | Demolition Plan and Drawings |  | C | C | P | S/P |  | n/a
22 | Utility Plan and Drawing |  | C | C | P | S/P |  | n/a
23 | Site Electrical Plan / Drawing |  | C | C | P | S/P |  | n/a
24 | Site Lighting Plan / Drawing |  | C | C | P | S/P |  | n/a
25 | Site Comm Plan / Drawing |  | C | C | P | S/P |  | n/a
26 | Erosion Control Plan / Drawing |  | C | C | P | S/P |  | n/a
27 | Stormwater Plan / Drawing |  | C | C | P | S/P |  | n/a
28 | Landscaping Plan / Drawing |  | C | C | P | S/P |  | n/a
29 | External Elevations (Structure) |  | C | C | P | S/P |  | n/a
30 | Interior Elevations (Structure) |  | C | P | S |  |  | n/a
31 | Interior Section Views |  | C | C | P | S/P |  | n/a
32 | Partition or Wall Types |  | C | C | S/P | S/P |  | n/a
33 | Finish Schedule |  | C | C | P | S/P |  | n/a
34 | Door Schedules |  | C | P | P | S/P |  | n/a
35 | Window Schedules |  | C | P | P | S/P |  | n/a
36 | Restroom Schedules |  | C | P | P | S/P |  | n/a
37 | Furniture Plans / Schedules / Drawings |  | C | C | P | S/P |  | n/a
38 | Signage Drawings / Schedules |  | C | P | P | S/P |  | n/a
39 | Fire Protection Plan / Drawings |  | C | C | P | S/P |  | n/a
40 | Room Layout Plan / Drawings |  | C | C | P | S/P |  | n/a
41 | Foundation Plan / Drawings |  | C | C | P | S/P |  | n/a
42 | Foundation Section / Details |  | C | C | P | S/P |  | n/a
43 | Structural Plan / Drawings |  | C | C | P | S/P |  | n/a
44 | Structural Section / Details |  | C | C | P | S/P |  | n/a
45 | Roof Plan Drawings / Details |  | C | C | P | S/P |  | n/a
46 | Material / Equipment Specs |  | C | C | P | S/P |  | n/a
47 | Building Envelope / Moisture Protection / Flashing Details |  | C | C | P | S/P |  | n/a
48 | Mechanical / HVAC Plan / Drawings |  | C | C | P | S/P |  | n/a
49 | Mechanical / HVAC Details |  | C | P | S/P |  |  | n/a
50 | Mechanical / HVAC Schedules |  | C | P | S/P |  |  | n/a
51 | Flow Control Designs |  | C | P | P | S/P |  | n/a
52 | Plumbing Plan / Drawings |  | C | C | P | S/P |  | n/a
53 | Plumbing Details |  | C | P | S/P |  |  | n/a
54 | Plumbing Riser Diagram |  | C | P | S/P |  |  | n/a
55 | One-Line Electrical Diagram |  | C | C | P | S/P |  | n/a
56 | Electrical Power Plan |  | C | C | P | S/P |  | n/a
57 | Interior Lighting Plan / Drawings |  | C | P | S/P |  |  | n/a
58 | Security Plan / Drawings |  | C | P | S/P |  |  | n/a
59 | Emergency Communication Plan / Drawings |  | C | P | S/P |  |  | n/a
60 | Life Safety Plan / Drawings |  | C | C | S/P | S |  | n/a
61 | Lightning Protection Plan |  | C | P | S/P |  |  | n/a
62 | Motor Control Diagram |  | C | P | S/P |  |  | n/a
63 | Lighting Control Drawings |  | C | P | S/P |  |  | n/a
64 | Lighting Schedules |  | C | P | S/P |  |  | n/a
65 | Electrical / Panel Drawings |  | C | P | S/P |  |  | n/a
66 | Equipment Schedule |  | C | P | S/P | S |  | n/a
67 | Info Systems / Telecom Plan |  | C | P | S/P |  |  | n/a
68 | Info Systems / Telecom Details |  | C | P | S/P |  |  | n/a

## Tab8-BOE Rationale
BOE rationale tab 8

## Appendix
0
Appendix

## Approvals & Update Log
Approvals
Role | Approved By (Type name) | Date | Comments (if authorized by email, embed…?)
AMO
F&A
IS&T
Other
Business Case Update Log This section is used to track content changes to the project's Business Case (BC). As the BC is updated at regular intervals, this section should only identify the date of any updates and only significant updates. If there is a need to determine the detailed changed variances, the previous saved version of the BC can be used for comparison.
Document Revision No. | Change in Content | Date | Updated By

## Template Version & Quality Ctrl (hidden)
Template Quality Information This section is used to track changes to the Business Case (BC) Template design by the The City of Winnipeg Corporate Asset Management Office.
Document Revision No. | Revisions | Date Released: | Released By:
4.1 | Old word formatted document. | 2016-04-05 | CAMO
5 | Convert template from word to excel format. | 2017-02-17 | CAMO
5WWD | Modified for WWD | 2017-03-08 | WWD-AMO

## CF Picklists (hidden)
| Departments | Investment Type
| Assessment & Taxation | Project
| Audit | Program
Chief Administrative Offices
Chief Financial Officer
| City Clerks | Funding Sources
| Community Services | Cash
| Corporate Finance | Debt
| Corporate Support Services | Other
Emergency Preparedness Program
Employee Benefits
| Fire Paramedic Service | Class of Estimate
| Legal Services | 1
| Mayor's Office | 2
| Planning, Property, and Development | 3
| Public Works | 4
| Water and Waste | 5
Winnipeg Fleet Management Agency
Winnipeg Police Service
Winnipeg Transit
Service Categories
Roadway Constr. & Maintenance - Bridge Constr & Maint
Roadway Constr. & Maintenance - Regl Streets Constr & Maint Contract
Roadway Constr. & Maintenance - Local Streets Constr & Maint
Roadway Constr. & Maintenance - Regl Sidewalk Constr & Maint
Roadway Constr. & Maintenance - Local Sidewalk Constr & Maint
Transp. Planning & Traffic Mgmt - Transportation Plan & Design Street Lighting
Transp. Planning & Traffic Mgmt - Traffic/Right of Way Mgt
Roadway Snow Rmvl & Ice Cont - Regl Streets Snow/Ice Removal
Roadway Snow Rmvl & Ice Cont - Local Streets Snow/Ice Removal
Roadway Snow Rmvl & Ice Cont - Sidewalk Snow & Ice Removal
Roadway Snow Rmvl & Ice Cont - Parks,Facility Snow,Ice Remove
Roadway Snow Rmvl & Ice Cont - Snow Disposal Sites
Water - Water Supply & Treatment
Water - Water Distribution
Wastewater - Wastewater Collection
Wastewater - Wastewater Treatment
Land Drainage & Flood Control - Flood Control
Land Drainage & Flood Control - Land Drainage
Solid Waste Collection & Disp - Solid Waste Collection
Solid Waste Collection & Disp - Solid Waste Disposal
Recycling & Waste Minimization - Recycling & Waste Minimization
Public Transit - Regular Transit
Public Transit - Handi-Transit
Public Transit - Chartered Bus & Special Events
Parks & Urban Forestry | Parks & Urban Forestry - Park Grass Maintenance
Parks & Urban Forestry - Park Amenity Maintenance
Parks & Urban Forestry - Athletic Field Maintenance
Parks & Urban Forestry - Park Pathway Maintenance
Parks & Urban Forestry - Park Planning/Development
Parks & Urban Forestry - Tree Planting
Parks & Urban Forestry - Tree Pruning & Removal
Parks & Urban Forestry - Dutch Elm Disease Control
Parks & Urban Forestry - Weed Control
Parks & Urban Forestry - Natural Areas Management
Parks & Urban Forestry - Playground Management
Parks & Urban Forestry - Boulevard Maintenance
City Beautification - Litter Collection
City Beautification - Public Gardens/Landscaping
City Beautification - OrnLight/Flags,Banners/PubArt
City Beautification - Graffiti Control
City Beautification - Regional Street Cleaning
City Beautification - Local Street Cleaning
Fleet Management SOA - Fleet Management
Parking Authority SOA - Parking Facilities
Parking Authority SOA - On Street Parking Enfrcmt
Parking Authority SOA - On-Street Parking
City Planning - Area Development & Renewal Planning
City Planning - City-wide Long Range Planning
Neighbourhood Revitalization - Community Development
Neighbourhood Revitalization - Housing Initiatives
Dev Approvals, Bldg Permits & Inspection - Res Dev Approvals & Inspection
Dev Approvals, Bldg Permits & Inspection - Com Dev Approvals & Inspection
Economic Development - Economic Development
Heritage Conservation - Heritage Conservation
Property Asset Management - Parking Facilities
Property Asset Management - Civic Accommodations
Property Asset Management - Pool Facilities
Property Asset Management - Arena Facilities
Property Asset Management - Recreation Centres
Property Asset Management - Community Centres
Property Asset Management - Land and Property
Cemeteries - Cemeteries
Organizational Support Services - Chief Administrative Offices
Organizational Support Services - Communications
Organizational Support Services - Financial Management
Organizational Support Services - Human Resource Management
Organizational Support Services - Info Technology Management
Organizational Support Services - Legal Services
Organizational Support Services - Production Services
Contact Centre - 311 - Contact Centre - 311
Disaster Preparedness & Resp - Disaster Preparedness & Response
Police Response - Police Response
Police Response - Policing
Police Response - Crime Investigation
Police Response - Police Training
Crime Prevention - Community Policing
Crime Prevention - Street Lighting
Crime Prevention - Park Policing
Crime Prevention - Crime Prevention Initiatives
Traffic Safety & Enforcement - Traffic Safety-Automated
Traffic Safety & Enforcement - Traffic Safety-Officer
Traffic Safety & Enforcement - Traffic Safety-Division
Fire and Rescue Response - Fire & Rescue Response
Fire and Rescue Response - Fire Investigation
Fire and Injury Prevention - Fire & Injury Prev Education
Fire and Injury Prevention - Fire Inspection
Medical Response - Medical Response
Medical Response - Medical Transfers
Disaster Preparedness & Resp - Disaster Preparedness & Response
Recreation - Aquatics Programs
Recreation - Ice/Skating Programs
Recreation - Sports, Fitness & Wellness
Recreation - Casual Recreation Facility Use
Recreation - Community Centre Grants
Recreation - Golf Courses
Community Health - Community Health Inspection
Community Health - Community By-law Enforcement
Community Health - Bicycle Recovery
Community Health - Citizen Crisis Response
Community Health - Social Grants
Libraries - Library Circulation
Libraries - Library Information
Libraries - Children's Library
Arts, Entertainment & Culture - Arts, Ent & Culture Grants
Arts, Entertainment & Culture - Arts, Ent & Culture Events
Arts, Entertainment & Culture - Zoo
Arts, Entertainment & Culture - Conservatory
Arts, Entertainment & Culture - Assiniboine Park Conservancy
Arts, Entertainment & Culture - Museums
Insect Control - Insect Control
Animal Services - SOA Animal Control & Care
Assessment, Taxation & Corporate - Assessment and Taxation
Assessment, Taxation & Corporate - Corporate
Council Services - Auditing
Council Services - Mayor and Council
Council Services - Archives-City Clerks
Council Services - Elections-City Clerks
Council Services - Citizen Access and Appeals
Council Services - Council Support-City Clerks

## WWD Picklists
Dept ID | Division | Service Categories | Location | Lat | Long | Essential | From/To | Scales
200652 | Engineering Services | Water - Water Supply & Treatment | 1199 Pacific Ave | 49.913 | -97.1769 | Legislative Compliance | VLVL | VL
200751 | Water Services | Water - Water Distribution | 360 McPhillips St | 49.9157 | -97.1712 | Health and Safety | VLL | L
200752 | Wastewater Services | Wastewater - Wastewater Treatment | 2230 Main St | 49.9517 | -97.1076 | Environmental Impact | VLM | M
200753 | Human Resources | Wastewater - Wastewater Collection | 552 Plinguet St | 49.8924 | -97.1003 |  | VLH | H
Multifunded | Information Services & Technology | Land Drainage & Flood Control - Flood Control | WTP-Springfield | 49.5058 | -96.565 | Quality | VLVH | VH
| Solid Waste Services | Land Drainage & Flood Control - Land Drainage | 1777 Brady Rd | 49.7602 | -97.2138 | Quality | LVL
| Environmental Services | Solid Waste Collection & Disp - Solid Waste Collection | 3000 Summit Rd | 49.921 | -97.3107 | Realiabity/Funcationality | LL
| Customer Services | Solid Waste Collection & Disp - Solid Waste Disposal | Other | Lat | Long | Condtion | LM
|  | Recycling & Waste Minimization - Recycling & Waste Minimization |  |  |  | Accessibilty | LH
| Funding Sources | [5 empty] | LVH
| Cash |  |  |  |  | Image | MVL
| Debt |  |  |  |  | Shine | ML
| Retained Earnings |  |  |  |  | Public Perception | MM
| Transfer from Sewer Utility | [5 empty] | MH
| Other |  |  |  |  | Growth | MVH
[6 empty] | Capacity / Headroom | HVL
| Class of Estimate |  |  |  |  | Demand | HL
| N/A | [5 empty] | HM
| Class 1 | [5 empty] | HH
| Class 2 | [5 empty] | HVH
| Class 3 | [5 empty] | VHVL
| Class 4 | [5 empty] | VHL
| Class 5 | [5 empty] | VHM
| Class 3 for study phase only | [5 empty] | VHH
| Class 3 for budget year only | [5 empty] | VHVH
Return Residual Funds
To general program
To other project