## HRRC Ph 3 - all
HRRC Phase 3
[10 empty] | 2020 |  | 2021 | [9 empty] | Estimated Costs | [7 empty] | Total
[5 empty] | Installation |  | Pipe |  |  | Inspection |  | Inspection |  | Consultant | Pipe Mods Contractor | Inspection Type | [5 empty] | Consultant | Pipe Mods Contractor | Inspection Type
Asset ID | Location | Service Type | Channel | Asset Function | Type | Year | Length | Dia | Mat | Type | Estimate | Type | Estimate |  |  | RFT | VA | UT | Pure EM | Sonar | RBS |  |  | RFT | VA | UT | Pure EM | Sonar | RBS
MA70016345 | Assiniboine Park Zoo Siphon | Sewer | Assiniboine | Siphon | Shallow Bury | 1967 | 116 | 200 | Steel |  |  | RBS | 6.8554 | In-House | [6 empty] | Yes | [7 empty] | 7 | 7
MA70058265 | Bridge of the Old Forks (east pipe) | Sewer | Assiniboine | Force Main | Bridge | 1996 | 176 | 500 | Steel |  |  | RFT | 256.6115 | External | Yes | Yes | [5 empty] | 48.8 | 153.4 | 54.4 | [5 empty] | 256.6
[12 empty] | UT | 6.9458 |  |  |  |  | Yes | [7 empty] | 7 |  |  |  | 7
MA70058225 | Bridge of the Old Forks (west pipe) | Sewer | Assiniboine | Force Main | Bridge | 1996 | 175 | 600 | Steel |  |  | RFT | 256.6115 | External | Yes | Yes | [5 empty] | 48.8 | 153.4 | 54.4 | [5 empty] | 256.6
[12 empty] | UT | 6.9458 |  |  |  |  | Yes | [7 empty] | 7 |  |  |  | 7
MA70020023 | Fort Garry Bridge (north pipe) | Sewer | Red | Siphon | River Bottom | 1973 | 250 | 700 | HDPE |  |  | RBS | 14.7746 | In-House | [6 empty] | Yes | [7 empty] | 15 | 15
[12 empty] | Sonar | 8.8647 | External | [5 empty] | Yes |  | 1.5 | [5 empty] | 7.5 |  | 9
MA70053063 | Fort Garry Bridge (south pipe) | Sewer | Red | Siphon | River Bottom | 1973 | 250 | 800 | HDPE |  |  | RBS | 14.7746 | In-House | [6 empty] | Yes | [7 empty] | 15 | 15
[12 empty] | Sonar | 8.8647 | External | [5 empty] | Yes |  | 1.5 | [5 empty] | 7.5 |  | 9
MA70057926 | Norwood Bridge | Sewer | Red | Force Main | Bridge | 1997 | 499 | 500 | Steel |  |  | RFT | 307.034 | External | Yes | Yes | [5 empty] | 65.1 | 187.5 | 54.4 | [5 empty] | 307
[12 empty] | UT | 6.9458 | External | Yes |  |  | Yes | [7 empty] | 7 |  |  |  | 7
MA70050829 | Provencher Bridge (north pipe) | Sewer | Red | Force Main | Bridge | 2005 | 426 | 300 | Steel | VA | 19.845 |  |  | External |  |  | Yes | [7 empty] | 20 |  |  |  |  | 20
MA70050831 | Provencher Bridge (south pipe) | Sewer | Red | Force Main | Bridge | 2005 | 845 | 300 | Steel | VA | 19.845 |  |  | External |  |  | Yes | [7 empty] | 20 |  |  |  |  | 20
MA70028006 | West Perimeter Bridge | Sewer | Assiniboine | Force Main | Buried | 2001 | 1244 | 400 | Steel |  |  | RFT | 423.298 | External | Yes | Yes | [5 empty] | 77 | 114 | 232 | [5 empty] | 423
[21 empty] | 2019-> | 242.7 | 608.3 | 508.2 | [5 empty] | 1359.2 | 395.2 | 40 | 21 | 0 | 15 | 37
[21 empty] | Contingencies-> | 50 | 100 | 0 | [5 empty] | 150
[21 empty] | Subtotal-> | 292.7 | 708.3 | 508.2 | [5 empty] | 1509.2
[21 empty] | MRST-> | 20.489 | 49.581 | 35.574 | [5 empty] | 105.644
[21 empty] | Subtotal-> | 313.189 | 757.881 | 543.774 | [5 empty] | 1614.844
[21 empty] | Corp Admin (1.25%)-> | 3.9149 | 9.4735 | 6.7972 | [5 empty] | 20.1855
[21 empty] | Corp Interest (2.00%)-> |  | 12.166 | [6 empty] | 12.166
[21 empty] | Total-> | 317.1039 | 779.5205 | 550.5712 | [5 empty] | 1647.1955
N/A | Dakota Feeder Main | Water | Seine | Feeder Main | Buried | 1964 | 1119 | 600 | PCCP | Pure EM | 216.1384 |  |  | External | Yes |  |  |  | Yes |  |  | 28.1 | 98.5 |  |  |  | 89.4 |  |  | 216
N/A | Rouge Road Feeder Main | Water | Sturgeon Creek | Feeder Main |  | 1987 | 1920 | 600 | PCCP | Pure EM | 255.0229 |  |  | External | Yes |  |  |  | Yes |  |  | 33.3 | 98.5 |  |  |  | 123.3 |  |  | 255.1
N/A | West End Feeder Main | Water | Omand's Creek | Feeder Main |  | 1987 | 1338 | 900 | PCCP | Pure EM | 226.7697 |  |  | External | Yes |  |  |  | Yes |  |  | 29.6 | 98.5 |  |  |  | 98.7 |  |  | 226.8
N/A | West End Feeder Main | Water | Truro Creek | Feeder Main |  | 1987 | 2179 | 900 | PCCP | Pure EM | 267.596 |  |  | External | Yes |  |  |  | Yes |  |  | 34.9 | 98.5 |  |  |  | 134.2 |  |  | 267.6
N/A | Haney Moray Feeder Main | Water | Assiniboine | Feeder Main |  | 1994 | 466 | 450 | CPP | Pure EM | 184.4385 |  |  | External | Yes |  |  |  | Yes |  |  | 24.1 | 98.5 |  |  |  | 61.9 |  |  | 184.5
N/A | Midtown Feeder Main | Water | Assiniboine | Feeder Main |  | 2012 | 1252 | 900 | PCCP | Pure EM | 222.5948 |  |  | External | Yes |  |  |  | Yes |  |  | 29 | 98.5 |  |  |  | 95.1 |  |  | 222.6
[21 empty] | 2019> | 179 | 591 | 602.6 | [5 empty] | 1372.6 | 0 | 0 | 0 | 602.6 | 0 | 0
[21 empty] | Contingencies-> | 50 | 100 | 0 | [5 empty] | 150
[21 empty] | Subtotal-> | 229 | 691 | 602.6 | [5 empty] | 1522.6
[21 empty] | MRST-> | 16.03 | 48.37 | 42.182 | [5 empty] | 106.582
[21 empty] | Subtotal-> | 245.03 | 739.37 | 644.782 | [5 empty] | 1629.182
[21 empty] | Corp Admin (1.25%)-> | 3.0629 | 9.2421 | 8.0598 | [5 empty] | 20.3648
[21 empty] | Corp Interest (2.00%)-> |  | 11.82 | [6 empty] | 11.82
[21 empty] | Total-> | 248.0929 | 760.4321 | 652.8418 | [5 empty] | 1661.3668
LEGEND
EM | Electromagnetic Inspections |  | PCCP | Prestressed Concrete Cylinder Pipe
RFT (EM) | Remote Field Technology (Ferrous metal pipes) |  | CPP | Concrete Pressure Pipe
MFL (EM) | Magnetic Flux Leakage (Ferrous metal pipes) |  | PVC | Polyvinyl Chloride
Pure EM | Electromagnetic Inspections on PCCP by Pure |  | HDPE | High Density Polyethylene
CCTV | Closed-Circuit Television Inspections |  | AC | Asbestos Cememt
Sonar | Sonar Inspections |  | CI | Cast Iron
RBS | River Bottom Scanning Inspections |  | [20] | Years of Remaining Life based on pipe corrosion only
UT | Ultrasonic Testing |  | (5) | Years before Re-Inspection
LT | Leak Testing (for presence of leaks, not locations) |  | é | Factor of Safety against Floatation. 2 is recommended
LDT | Leak Detection Testing (Correlators, Smart Ball) |  | CIPP | Cured-In-Place Pipe
MT | Material Testing |  | Rehab | Rehabilitation or Replacement Required
VA | Visual Assessment |  | Geotech | Riverbank Rehabilitation required.
Note on F5: Bridge means pipe is suspended from bridge. Buried means pipe had at least 1m of cover after construction. Not Fully Buried means portions of the pipe were left exposed after construction. River Bottom means pipe was laid on the river bottom and fully exposed. Shallow Bury means pipe had areas with less than 1m of cover after construction.
Note on B6: Delaurier, Armand: This asset doesn't belong to WWD, therefore AMB is not required for geotech work, as confirmed by discussion between CW & AD on March 8, 2018. Do not include Riverbank rehab in Investment Planning (BCs). AMB will still fund internal pipe inspections and River Bottom Scanning projects. Email sent to Kendall Thiessen on March 9, 2018 indicating closure of this work.
Note on N6: Delaurier, Armand: $0.040K/m for RBS Inspection in 2013 dollars. No allowance for Engineering as can be done in-house. Add 5%/year
Note on N7: Armand L. Delaurier: Consultant = $48.8k 0.5*(2*0.75*(51*(1.05^(2021-2016)))) Pipe Mods = $153.4k 0.5*((1*(59*(1.05^(2021-2018))))+(2*(103*(1.05^(2021-2018))))) Insp = $54.4k 0.5*(2*(47*(1.05^(2021-2018))))
Note on N9: Armand L. Delaurier: Consultant = $48.8k 0.5*(2*0.75*(51*(1.05^(2021-2016)))) Pipe Mods = $153.4k 0.5*((1*(59*(1.05^(2021-2018))))+(2*(103*(1.05^(2021-2018))))) Insp = $54.4k 0.5*(2*(47*(1.05^(2021-2018))))
Note on N11: Delaurier, Armand: $0.040K/m for RBS Inspection and $0.020K/m for Sonar Inspections in 2013 dollars. No allowance for Engineering for RBS as can be done in-house; plus 20% Engineering for Sonar. Add 5%/year
Note on N12: Delaurier, Armand: $0.040K/m for RBS Inspection and $0.020K/m for Sonar Inspections in 2013 dollars. No allowance for Engineering for RBS as can be done in-house; plus 20% Engineering for Sonar. Add 5%/year
Note on N13: Delaurier, Armand: $0.040K/m for RBS Inspection and $0.020K/m for Sonar Inspections in 2013 dollars. No allowance for Engineering for RBS as can be done in-house; plus 20% Engineering for Sonar. Add 5%/year
Note on N14: Delaurier, Armand: $0.040K/m for RBS Inspection and $0.020K/m for Sonar Inspections in 2013 dollars. No allowance for Engineering for RBS as can be done in-house; plus 20% Engineering for Sonar. Add 5%/year
Note on N15: Armand L. Delaurier: Consultant = $65.1k (51*(1.05^(2021-2016))) Pipe Mods = $187.5k (59*(1.05^(2021-2018)))+(103*(1.05^(2021-2018))) Insp = $54.4k (47*(1.05^(2021-2018)))
Note on L17: Visual Assessment (VA) Force main Inspection (2018 Dollars + 5% annually): 2 peolple x 1 day x 10hrs x $200/hr = $4,000 Expenses/Misc equipment/tools = $2,000 Field Support = $2,000 Office inspection review & desktop analysis = $5,000 Final Report = $5,000 Total = $18,000 (in 2018)
Note on L18: Visual Assessment (VA) Force main Inspection (2018 Dollars + 5% annually): 2 peolple x 1 day x 10hrs x $200/hr = $4,000 Expenses/Misc equipment/tools = $2,000 Field Support = $2,000 Office inspection review & desktop analysis = $5,000 Final Report = $5,000 Total = $18,000 (in 2018)
Note on N19: Delaurier, Armand: RFEC Inspection in 2014 dollars which includes for Engineering. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown. For this site, the RFT inspection cost was cut in half as 1244m is length from MH to pumping station; likely can install wyes at Sta 34+70 & 39+70 (DWGS 4787 & 4788), to make length about 500m. RFT Consultant = $77k Pipe Mods = $114k Insp = $232k Advanced up to 2021 in mid-2019 as pipe material is steel; this decision was made after BC 0216 was revised. NOTE: The inspection was advanced from 2028 to 2021 due to the St. Vital Bridge Steel pipe failure.
Note on H29: Delaurier, Armand: Changed from 187m to 1119m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J29: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L29: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H30: Delaurier, Armand: Changed from 49m to 1920m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J30: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L30: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H31: Delaurier, Armand: Changed from 53m to 1338m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J31: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L31: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H32: Delaurier, Armand: Changed from 95m to 2179m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J32: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L32: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H33: Delaurier, Armand: Changed from 301m to 466m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J33: AWWA C303 Concrete Pressure Pipe (Bar-Wrapped)
Note on L33: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H34: Delaurier, Armand: Changed from 104m to 1252m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J34: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L34: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.

## HRRC Ph 3 - RFP###
HRRC Phase 3
[10 empty] | 2020 |  | 2021 | [9 empty] | Estimated Costs | [7 empty] | Total
[5 empty] | Installation |  | Pipe |  |  | Inspection |  | Inspection |  | Consultant | Pipe Mods Contractor | Inspection Type | [5 empty] | Consultant | Pipe Mods Contractor | Inspection Type
Asset ID | Location | Service Type | Channel | Asset Function | Type | Year | Length | Dia | Mat | Type | Estimate | Type | Estimate |  |  | RFT | VA | UT | Pure EM | Sonar | RBS |  |  | RFT | VA | UT | Pure EM | Sonar | RBS
MA70058265 | Bridge of the Old Forks (east pipe) | Sewer | Assiniboine | Force Main | Bridge | 1996 | 176 | 500 | Steel |  |  | RFT | 256.6115 | External | Yes | Yes | [5 empty] | 48.8 | 153.4 | 54.4 | [5 empty] | 256.6
[12 empty] | UT | 6.9458 |  |  |  |  | Yes | [7 empty] | 7 |  |  |  | 7
MA70058225 | Bridge of the Old Forks (west pipe) | Sewer | Assiniboine | Force Main | Bridge | 1996 | 175 | 600 | Steel |  |  | RFT | 256.6115 | External | Yes | Yes | [5 empty] | 48.8 | 153.4 | 54.4 | [5 empty] | 256.6
[12 empty] | UT | 6.9458 |  |  |  |  | Yes | [7 empty] | 7 |  |  |  | 7
MA70020023 | Fort Garry Bridge (north pipe) | Sewer | Red | Siphon | River Bottom | 1973 | 250 | 700 | HDPE |  |  | Sonar | 8.8647 | External | [5 empty] | Yes |  | 1.5 | [5 empty] | 7.5 |  | 9
MA70053063 | Fort Garry Bridge (south pipe) | Sewer | Red | Siphon | River Bottom | 1973 | 250 | 800 | HDPE |  |  | Sonar | 8.8647 | External | [5 empty] | Yes |  | 1.5 | [5 empty] | 7.5 |  | 9
MA70057926 | Norwood Bridge | Sewer | Red | Force Main | Bridge | 1997 | 499 | 500 | Steel |  |  | RFT | 307.034 | External | Yes | Yes | [5 empty] | 65.1 | 187.5 | 54.4 | [5 empty] | 307
[12 empty] | UT | 6.9458 | External | Yes |  |  | Yes | [7 empty] | 7 |  |  |  | 7
MA70050829 | Provencher Bridge (north pipe) | Sewer | Red | Force Main | Bridge | 2005 | 426 | 300 | Steel | VA | 19.845 |  |  | External |  |  | Yes | [7 empty] | 20 |  |  |  |  | 20
MA70050831 | Provencher Bridge (south pipe) | Sewer | Red | Force Main | Bridge | 2005 | 845 | 300 | Steel | VA | 19.845 |  |  | External |  |  | Yes | [7 empty] | 20 |  |  |  |  | 20
MA70028006 | West Perimeter Bridge | Sewer | Assiniboine | Force Main | Buried | 2001 | 1244 | 400 | Steel |  |  | RFT | 423.298 | External | Yes | Yes | [5 empty] | 77 | 114 | 232 | [5 empty] | 423
[20 empty] | 2019-> |  | 242.7 | 608.3 | 471.2 | [5 empty] | 1322.2 | 395.2 | 40 | 21 | 0 | 15 | 0
[20 empty] | Contingencies-> |  | 50 | 100 | 0 | [5 empty] | 150
[20 empty] | Subtotal-> |  | 292.7 | 708.3 | 471.2 | [5 empty] | 1472.2
[20 empty] | MRST-> |  | 20.489 | 49.581 | 32.984 | [5 empty] | 103.054
[20 empty] | Subtotal-> |  | 313.189 | 757.881 | 504.184 | [5 empty] | 1575.254
[20 empty] | Corp Admin (1.25%)-> |  | 3.9149 | 9.4735 | 6.3023 | [5 empty] | 19.6907
[20 empty] | Corp Interest (2.00%)-> |  |  | 12.166 | [6 empty] | 12.166
[20 empty] | Total-> |  | 317.1039 | 779.5205 | 510.4863 | [5 empty] | 1607.1107
N/A | Dakota Feeder Main | Water | Seine | Feeder Main | Buried | 1964 | 1119 | 600 | PCCP | Pure EM | 216.1384 |  |  | External | Yes |  |  |  | Yes |  |  | 28.1 | 98.5 |  |  |  | 89.4 |  |  | 216
N/A | Rouge Road Feeder Main | Water | Sturgeon Creek | Feeder Main |  | 1987 | 1920 | 600 | PCCP | Pure EM | 255.0229 |  |  | External | Yes |  |  |  | Yes |  |  | 33.3 | 98.5 |  |  |  | 123.3 |  |  | 255.1
N/A | West End Feeder Main | Water | Omand's Creek | Feeder Main |  | 1987 | 1338 | 900 | PCCP | Pure EM | 226.7697 |  |  | External | Yes |  |  |  | Yes |  |  | 29.6 | 98.5 |  |  |  | 98.7 |  |  | 226.8
N/A | West End Feeder Main | Water | Truro Creek | Feeder Main |  | 1987 | 2179 | 900 | PCCP | Pure EM | 267.596 |  |  | External | Yes |  |  |  | Yes |  |  | 34.9 | 98.5 |  |  |  | 134.2 |  |  | 267.6
N/A | Haney Moray Feeder Main | Water | Assiniboine | Feeder Main |  | 1994 | 466 | 450 | CPP | Pure EM | 184.4385 |  |  | External | Yes |  |  |  | Yes |  |  | 24.1 | 98.5 |  |  |  | 61.9 |  |  | 184.5
N/A | Midtown Feeder Main | Water | Assiniboine | Feeder Main |  | 2012 | 1252 | 900 | PCCP | Pure EM | 222.5948 |  |  | External | Yes |  |  |  | Yes |  |  | 29 | 98.5 |  |  |  | 95.1 |  |  | 222.6
[20 empty] | 2019> |  | 179 | 591 | 602.6 | [5 empty] | 1372.6 | 0 | 0 | 0 | 602.6 | 0 | 0
[20 empty] | Contingencies-> |  | 50 | 100 | 0 | [5 empty] | 150
[20 empty] | Subtotal-> |  | 229 | 691 | 602.6 | [5 empty] | 1522.6
[20 empty] | MRST-> |  | 16.03 | 48.37 | 42.182 | [5 empty] | 106.582
[20 empty] | Subtotal-> |  | 245.03 | 739.37 | 644.782 | [5 empty] | 1629.182
[20 empty] | Corp Admin (1.25%)-> |  | 3.0629 | 9.2421 | 8.0598 | [5 empty] | 20.3648
[20 empty] | Corp Interest (2.00%)-> |  |  | 11.82 | [6 empty] | 11.82
[20 empty] | Total-> |  | 248.0929 | 760.4321 | 652.8418 | [5 empty] | 1661.3668
LEGEND
EM | Electromagnetic Inspections |  | PCCP | Prestressed Concrete Cylinder Pipe
RFT (EM) | Remote Field Technology (Ferrous metal pipes) |  | CPP | Concrete Pressure Pipe
MFL (EM) | Magnetic Flux Leakage (Ferrous metal pipes) |  | PVC | Polyvinyl Chloride
Pure EM | Electromagnetic Inspections on PCCP by Pure |  | HDPE | High Density Polyethylene
CCTV | Closed-Circuit Television Inspections |  | AC | Asbestos Cememt
Sonar | Sonar Inspections |  | CI | Cast Iron
RBS | River Bottom Scanning Inspections |  | [20] | Years of Remaining Life based on pipe corrosion only
UT | Ultrasonic Testing |  | (5) | Years before Re-Inspection
LT | Leak Testing (for presence of leaks, not locations) |  | é | Factor of Safety against Floatation. 2 is recommended
LDT | Leak Detection Testing (Correlators, Smart Ball) |  | CIPP | Cured-In-Place Pipe
MT | Material Testing |  | Rehab | Rehabilitation or Replacement Required
VA | Visual Assessment |  | Geotech | Riverbank Rehabilitation required.
Note on F5: Bridge means pipe is suspended from bridge. Buried means pipe had at least 1m of cover after construction. Not Fully Buried means portions of the pipe were left exposed after construction. River Bottom means pipe was laid on the river bottom and fully exposed. Shallow Bury means pipe had areas with less than 1m of cover after construction.
Note on N6: Armand L. Delaurier: Consultant = $48.8k 0.5*(2*0.75*(51*(1.05^(2021-2016)))) Pipe Mods = $153.4k 0.5*((1*(59*(1.05^(2021-2018))))+(2*(103*(1.05^(2021-2018))))) Insp = $54.4k 0.5*(2*(47*(1.05^(2021-2018))))
Note on N8: Armand L. Delaurier: Consultant = $48.8k 0.5*(2*0.75*(51*(1.05^(2021-2016)))) Pipe Mods = $153.4k 0.5*((1*(59*(1.05^(2021-2018))))+(2*(103*(1.05^(2021-2018))))) Insp = $54.4k 0.5*(2*(47*(1.05^(2021-2018))))
Note on N10: Delaurier, Armand: $0.040K/m for RBS Inspection and $0.020K/m for Sonar Inspections in 2013 dollars. No allowance for Engineering for RBS as can be done in-house; plus 20% Engineering for Sonar. Add 5%/year
Note on N11: Delaurier, Armand: $0.040K/m for RBS Inspection and $0.020K/m for Sonar Inspections in 2013 dollars. No allowance for Engineering for RBS as can be done in-house; plus 20% Engineering for Sonar. Add 5%/year
Note on N12: Armand L. Delaurier: Consultant = $65.1k (51*(1.05^(2021-2016))) Pipe Mods = $187.5k (59*(1.05^(2021-2018)))+(103*(1.05^(2021-2018))) Insp = $54.4k (47*(1.05^(2021-2018)))
Note on L14: Visual Assessment (VA) Force main Inspection (2018 Dollars + 5% annually): 2 peolple x 1 day x 10hrs x $200/hr = $4,000 Expenses/Misc equipment/tools = $2,000 Field Support = $2,000 Office inspection review & desktop analysis = $5,000 Final Report = $5,000 Total = $18,000 (in 2018)
Note on L15: Visual Assessment (VA) Force main Inspection (2018 Dollars + 5% annually): 2 peolple x 1 day x 10hrs x $200/hr = $4,000 Expenses/Misc equipment/tools = $2,000 Field Support = $2,000 Office inspection review & desktop analysis = $5,000 Final Report = $5,000 Total = $18,000 (in 2018)
Note on N16: Delaurier, Armand: RFEC Inspection in 2014 dollars which includes for Engineering. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown. For this site, the RFT inspection cost was cut in half as 1244m is length from MH to pumping station; likely can install wyes at Sta 34+70 & 39+70 (DWGS 4787 & 4788), to make length about 500m. RFT Consultant = $77k Pipe Mods = $114k Insp = $232k Advanced up to 2021 in mid-2019 as pipe material is steel; this decision was made after BC 0216 was revised. NOTE: The inspection was advanced from 2028 to 2021 due to the St. Vital Bridge Steel pipe failure.
Note on H26: Delaurier, Armand: Changed from 187m to 1119m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J26: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L26: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H27: Delaurier, Armand: Changed from 49m to 1920m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J27: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L27: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H28: Delaurier, Armand: Changed from 53m to 1338m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J28: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L28: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H29: Delaurier, Armand: Changed from 95m to 2179m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J29: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L29: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H30: Delaurier, Armand: Changed from 301m to 466m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J30: AWWA C303 Concrete Pressure Pipe (Bar-Wrapped)
Note on L30: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.
Note on H31: Delaurier, Armand: Changed from 104m to 1252m on June 21, 2019, based on revised lengths as determined by Matt N using GIS.
Note on J31: AWWA C301 Pre-stressed Concrete Cylinder Pipe
Note on L31: Delaurier, Armand: Pure EM Inspection using 2013 estimate. $100K (Mob/Demob=$10K; Prep=$7K; Reports=$10K; Distress Curves=$3K; Mods+Cleaning =$70K)/site + $30/m inspection. Includes 15% for In-House Engineering & Contingencies. Add 5%/year. See 'Insp & Re-Insp Rationale' Tab for cost breakdown.

## RFP FEE Structure
FORM B(R1): PRICES
See B8 clause in tender document)
Task | Spec Ref | Fee Basis | Fee
1. Project Management | D5.7 | Fixed
2. Consultant Progress Reports | D5.8 | Fixed
3. Project Development | D5.9 | Fixed
4. Technical Memorandums | D5.10 | Fixed
5. Inspection Program Workshops | D5.11 | Fixed
6. Drawings and Tender Preparation | D5.12
6.1 Pipeline Modifications and Support Tender |  | Fixed
6.2 Pipeline Inspection Tender No. 1 |  | Fixed
6.3 Pipeline Inspection Tender No. 2 |  | Fixed
6.4 Pipeline Inspection Tender No. 3 |  | Fixed
7. Procurement Process | D5.13
7.1 Pipeline Modifications and Support Tender |  | Fixed
7.2 Pipeline Inspection Tender No. 1 |  | Fixed
7.3 Pipeline Inspection Tender No. 2 |  | Fixed
7.4 Pipeline Inspection Tender No. 3 |  | Fixed
8. Construction Meeting Minutes | D5.14 | Fixed
9. Non-Resident Contract Administration | D5.15.1
9.1 Old Forks Bridge (east and west pipes) |  | Fixed
9.2 Provencher Bridge (north and south pipes) |  | Fixed
9.3 Fort Garry Bridge (north and south pipes) |  | Fixed
9.4 Norwood Bridge |  | Fixed
9.5 West Perimeter Bridge |  | Fixed
9.6 Dakota (Seine River) |  | Fixed
9.7 Rouge Road (Sturgeon Creek) |  | Fixed
9.8 West End (Omand's Creek) |  | Fixed
9.9 West End (Truro Creek) |  | Fixed
9.10 Haney Moray (Assiniboine River) |  | Fixed
10. Resident Contract Administration | D5.15.2
10.1 Old Forks Bridge (east and west pipes) |  | Fixed
10.2 Provencher Bridge (north and south pipes) |  | Fixed
10.3 Fort Garry Bridge (north and south pipes) |  | Fixed
10.4 Norwood Bridge |  | Fixed
10.5 West Perimeter Bridge |  | Fixed
10.6 Dakota (Seine River) |  | Fixed
10.7 Rouge Road (Sturgeon Creek) |  | Fixed
10.8 West End (Omand's Creek) |  | Fixed
10.9 West End (Truro Creek) |  | Fixed
10.10 Haney Moray (Assiniboine River) |  | Fixed
11. Condition Assessment | D5.16
11.1 Old Forks Bridge (east and west pipes) |  | Fixed
11.2 Provencher Bridge (north and south pipes) |  | Fixed
11.3 Fort Garry Bridge (north and south pipes) |  | Fixed
11.4 Norwood Bridge |  | Fixed
11.5 West Perimeter Bridge |  | Fixed
11.6 Dakota (Seine River) |  | Fixed
11.7 Rouge Road (Sturgeon Creek) |  | Fixed
11.8 West End (Omand's Creek) |  | Fixed
11.9 West End (Truro Creek) |  | Fixed
11.10 Haney Moray (Assiniboine River) |  | Fixed
12. Record Drawings | D5.17 | Fixed
13. Summary Report | D5.18 | Fixed
14. Project Close-Out Presentation | D5.19 | Fixed
15. Consultant Progress Reports Incentive | D5.20 | Fixed | 5000
16. Technical Memorandums Incentive | D5.21 | Fixed | 2500
17. Construction Meeting Minutes Incentive | D5.22 | Fixed | 2500
18. Draft Summary Report Incentive | D5.23 | Fixed | 2500
19. Final Summary Report Incentive | D5.24 | Fixed | 2500
20. Emergency Investigations | D5.25 | Time Based | 50000
21. Underground Structures | B8.5 | Fixed | 10000
22. Material Testing | B8.5 | Fixed | 25000
TOTAL FEES (GST estra)(in numbers) |  | 100000
Name of Bidder