## Unit prices
FORM B:PRICES
(See B9 clause in tender document)
UNIT PRICES
Item | Description | Spec. Ref | Fee Basis | Approximate Quantity | Unit Price | Disbursement | Total Fee
1 | Project Management | D7 | Fixed Fee | 1 |  |  | 0
2 | Consultant Progress Reports | D8 | Fixed Fee | 1 |  |  | 0
3 | Engagement Consultations | D9 | Fixed Fee | 1 |  |  | 0
4 | Wastewater Hydraulic Modelling Services | D10 | Fixed Fee | 1 |  |  | 0
Contract 1 - River Crossing Twin Force Mains
5 | Detailed Engineering Design | D11, D12 | Fixed Fee | 1 |  |  | 0
6 | Construction Documents | D17, D18 | Fixed Fee | 1 |  |  | 0
7 | RFQ and Procurement Process | D21, D22 | Fixed Fee | 1 |  |  | 0
8 | Contract Administration Services - Non-Resident | D24 | Fixed Fee | 1 |  |  | 0
9 | Contract Administration Services - Resident | D26 | Fixed Fee | 1 |  |  | 0
10 | Contract Administration - Resident Tunnel Drive Site Hours | D27 | Time-Based | 4100 |  |  | 0
11 | Record Documents and Project Close-Out | D32 | Fixed Fee | 1 |  |  | 0
Contract 2 - Downstream Gravity Sewer Interceptor
12 | Detailed Engineering Design | D11, D13 | Fixed Fee | 1 |  |  | 0
13 | Construction Documents | D17, D18 | Fixed Fee | 1 |  |  | 0
14 | RFQ and Procurement Process | D21, D22 | Fixed Fee | 1 |  |  | 0
15 | Contract Administration Services - Non-Resident | D24 | Fixed Fee | 1 |  |  | 0
16 | Contract Administration Services - Resident | D26 | Fixed Fee | 1 |  |  | 0
17 | Contract Administration - Resident Tunnel Drive Site Hours | D28 | Time-Based | 5400 |  |  | 0
18 | Record Documents and Project Close-Out | D32 | Fixed Fee | 1 |  |  | 0
Contract 3 - Linacre Lift Station
19 | Detailed Engineering Design | D11, D14 | Fixed Fee | 1 |  |  | 0
20 | Construction Documents | D17, D19 | Fixed Fee | 1 |  |  | 0
21 | RFQ and Procurement Process | D21, D22 | Fixed Fee | 1 |  |  | 0
22 | PLC & HMI Programming | D23 | Fixed Fee | 1 |  |  | 0
23 | Contract Administration Services - Non-Resident | D24 | Fixed Fee | 1 |  |  | 0
24 | Factory Acceptance Testing (FAT) | D25 | Fixed Fee | 1 |  |  | 0
25 | Contract Administration Services - Resident | D26 | Fixed Fee | 1 |  |  | 0
26 | Contract Administration - Resident Site Hours | D29 | Time-Based | 3400 |  |  | 0
27 | Commissioning | D31 | Fixed Fee | 1 |  |  | 0
28 | Record Documents and Project Close-Out | D32, D33 | Fixed Fee | 1 |  |  | 0
Contract 4 - Upstream Sewer Work
29 | Detailed Engineering Design | D11, D15 | Fixed Fee | 1 |  |  | 0
30 | Construction Documents | D17, D18 | Fixed Fee | 1 |  |  | 0
31 | Procurement Process | D22 | Fixed Fee | 1 |  |  | 0
32 | Contract Administration Services - Non-Resident | D24 | Fixed Fee | 1 |  |  | 0
33 | Contract Administration Services - Resident | D26 | Fixed Fee | 1 |  |  | 0
34 | Contract Administration - Resident Tunnel Drive Site Hours | D30 | Time-Based | 1700 |  |  | 0
35 | Record Documents and Project Close-Out | D32 | Fixed Fee | 1 |  |  | 0
Contract 5 - Kilkenny Lift Station Demolition
36 | Detailed Engineering Design | D11, D16 | Fixed Fee | 1 |  |  | 0
37 | Demolition Documents | D17, D20 | Fixed Fee | 1 |  |  | 0
38 | Procurement Process | D22 | Fixed Fee | 1 |  |  | 0
39 | Contract Administration Services - Non-Resident | D24 | Fixed Fee | 1 |  |  | 0
40 | Contract Administration Services - Resident | D26 | Fixed Fee | 1 |  |  | 0
41 | Record Documents and Project Close-Out | D32 | Fixed Fee | 1 |  |  | 0
42 | Heritage Work Allowance | D34 | Allowance | 1 | 300000 | 0 | 300000
43 | Geotechnical Work Allowance | D35 | Allowance | 1 | 500000 | 0 | 500000
44 | Additional Work Allowance | D36 | Allowance | 1 | 500000 | 0 | 500000
TOTAL BID PRICE (GST & MRST extra) (in numbers) |  |  |  |  | 1300000
Name of Bidder
Note on C2: Insert reference to "Prices" clause from the "Bidding Procedures". Also Revise the Header by inserting Tender # and revising the Tender Version number to match the Tender template used.
Note on A3: For Tenders with Budgets enter here. Format is BUDGET: $###.###.##