## Person Hours & Engineering Fees
FORM P: PERSON HOURS (see B10 clause in RFP document)
Person Hours and Estimated Fees
Phase and Task Description | Role/ Project Role: | Project Manager | Contract Administrator | Automation Lead Engineer | Civil Lead Engineer | Electrical Lead Engineer | Geotechnical Lead Engineer | Mechanical Lead Engineer | PLC Programming Lead Engineer | Process Lead Engineer | Structural Lead Engineer | Discipline Support | Discipline Drafting | Clerical | Summary
| Name: | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | (enter name) | Total Hours | Labour Fees | Allowable Disbursements | Total Fees
Hourly Rate:
PRELIMINARY ENGINEERING DESIGN
1. Kickoff & Biweekly Design Meetings & Meeting Minutes (8 Total) | [14 empty] | 0 | 0 | 0 | 0
2. Site Visits (Minimum 2) | [14 empty] | 0 | 0 | 0 | 0
3. Hydraulic System Curve and Proposed Pump Curves | [14 empty] | 0 | 0 | 0 | 0
4. Preliminary Engineering Design (Drawings) | [14 empty] | 0 | 0 | 0 | 0
5. Preliminary Design Report & Submission | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
DETAILED ENGINEERING DESIGN
1. Biweekly Design Meetings & Meeting Minutes (10 Total) | [14 empty] | 0 | 0 | 0 | 0
2. 66% Design Submission & Review | [14 empty] | 0 | 0 | 0 | 0
3. 99% Design Submission & Review | [14 empty] | 0 | 0 | 0 | 0
4. 100% Design Submission & Review | [14 empty] | 0 | 0 | 0 | 0
5. Architectural / Building Design | [14 empty] | 0 | 0 | 0 | 0
6. Civil and Municipal Engineering | [14 empty] | 0 | 0 | 0 | 0
7. Structural Engineering | [14 empty] | 0 | 0 | 0 | 0
8. Geotechnical Engineering | [14 empty] | 0 | 0 | 0 | 0
9. Mechanical Engineering - Process Pumping & Piping | [14 empty] | 0 | 0 | 0 | 0
10. Mechanical Engineering - HVAC System | [14 empty] | 0 | 0 | 0 | 0
11. Electrical Engineering | [14 empty] | 0 | 0 | 0 | 0
12. Automation & Instrumentation Engineering | [14 empty] | 0 | 0 | 0 | 0
13. St. Charles Engineering Design | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
CONSTRUCTION AND DEMOLITION DOCUMENTS
1. General Construction Documents | [14 empty] | 0 | 0 | 0 | 0
2. Geotechnical Report | [14 empty] | 0 | 0 | 0 | 0
3. Architectural / Building Construction Drawings | [14 empty] | 0 | 0 | 0 | 0
4. Civil Construction Drawings | [14 empty] | 0 | 0 | 0 | 0
5. Structural Construction Drawings | [14 empty] | 0 | 0 | 0 | 0
6. Mechanical Construction Drawings | [14 empty] | 0 | 0 | 0 | 0
7. Electrical Construction Documents | [14 empty] | 0 | 0 | 0 | 0
8. Automation Construction Documents | [14 empty] | 0 | 0 | 0 | 0
9. Process Construction Documents | [14 empty] | 0 | 0 | 0 | 0
10. St. Charles Demolition Documents | [14 empty] | 0 | 0 | 0 | 0
11. Specifications | [14 empty] | 0 | 0 | 0 | 0
12. Schneider Electric Equipment Procurement | [14 empty] | 0 | 0 | 0 | 0
13. Pumping Equipment Tender | [14 empty] | 0 | 0 | 0 | 0
14. Construction and Demolition Tender | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
PROCUREMENT PROCESS
1. Submit Construction and Pumping Equipment Procurement Packages | [14 empty] | 0 | 0 | 0 | 0
2. Tender Site Visits & Agenda (4 total) | [14 empty] | 0 | 0 | 0 | 0
3. Provide Response to Bidders | [14 empty] | 0 | 0 | 0 | 0
4. Review Bid Submissions & Recommend Award | [14 empty] | 0 | 0 | 0 | 0
5. Pre-Award Meeting and Meeting Minutes | [14 empty] | 0 | 0 | 0 | 0
6. Submit Schneider Electric Equipment Package | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
CORNISH LIFT STATION PLC PROGRAMMING
1. PLC Programming Meetings & Meeting Minutes | [14 empty] | 0 | 0 | 0 | 0
2. Schneider Electric M580 PLC Report | [14 empty] | 0 | 0 | 0 | 0
4. Schneider Electric M580 PLC Programming & HMI Touchscreen | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
CONTRACT ADMINISTRATION SERVICES – NON-RESIDENT
1. Long Lead Equipment Procurement Kickoff & Monthly Meetings and Meeting Minutes (6 Total) | [14 empty] | 0 | 0 | 0 | 0
2. Construction and Demolition Tender Kickoff & Monthly Meetings and Meeting Minutes (21 Total) | [14 empty] | 0 | 0 | 0 | 0
3. General Contract Admin Work (PCNs, CWOs, RFIs, progress estimates, field instructions, etc.) | [14 empty] | 0 | 0 | 0 | 0
4. Review Contractor Submittals | [14 empty] | 0 | 0 | 0 | 0
5. Review and Approve Contractor Shop Drawings (50 total) | [14 empty] | 0 | 0 | 0 | 0
6. Review Contractor Temporary Bypass Pumping Plan | [14 empty] | 0 | 0 | 0 | 0
7. In-Person PLC Control Panel & VFD FAT Testing (12 hours) | [14 empty] | 0 | 0 | 0 | 0
8. Equipment Suppliers Payment Schedules and Monthly Contractor Progress Payments | [14 empty] | 0 | 0 | 0 | 0
9. Condition Assessment Report | [14 empty] | 0 | 0 | 0 | 0
10. Assist in Obtaining City Development, Building and Waterway Permits | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
CONTRACT ADMINISTRATION SERVICES – RESIDENT
1. Project Management Services | [14 empty] | 0 | 0 | 0 | 0
2. Regular On Site Inspections & Reports (35 total) | [14 empty] | 0 | 0 | 0 | 0
3. Prepare and Update Deficiency Log | [14 empty] | 0 | 0 | 0 | 0
4. Prepare and Review Contractor Operational Shutdown Summary (OSS) Plans & Site Hours (16 hours) | [14 empty] | 0 | 0
5. Wet Well Inspection and Technical Memorandum | [14 empty] | 0 | 0
6. On Site Inspections for Critical Stages | [14 empty] | 0 | 0 | 0 | 0
7. Final Inspections and Construction Acceptance | [14 empty] | 0 | 0 | 0 | 0
8. Authorities Having Jurisdiction Site Visits & Follow Up | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
CORNISH LIFT STATION COMMISSIONING
1. Review and Approve Contractor Commissioning Plan | [14 empty] | 0 | 0 | 0 | 0
2. Commissioning Field Reports (3 total) | [14 empty] | 0 | 0 | 0 | 0
3. Commissioning Site Time (88 hours - Electrical, Instrumentation, Mechanical, Process, PLC Programming) | [14 empty] | 0 | 0 | 0 | 0
4. Preparing and Pre-Filling Forms, Filling in PLC Forms | [14 empty] | 0 | 0 | 0 | 0
5. Testing All I/O Points to SCADA (8 hours) | [14 empty] | 0 | 0 | 0 | 0
6. Review Contractor Type-Written Checklist Forms | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
RECORD DOCUMENTS AND PROJECT CLOSE-OUT
1. Training Sessions and Permits Close-Out | [14 empty] | 0 | 0 | 0 | 0
2. Review and Approve Contractor Operations & Maintenance Manual | [14 empty] | 0 | 0 | 0 | 0
3. Arc Flash Report and Labels | [14 empty] | 0 | 0 | 0 | 0
4. Warranty Services | [14 empty] | 0 | 0 | 0 | 0
5. Asset Equipment List | [14 empty] | 0 | 0 | 0 | 0
6. Cancel / Supersede Existing City Drawings | [14 empty] | 0 | 0 | 0 | 0
7. Prepare Record Documents | [14 empty] | 0 | 0 | 0 | 0
8. Preliminary & Final Record Drawing Submission & Review | [14 empty] | 0 | 0 | 0 | 0
9. Print Full Size Plots and Courier Package | [14 empty] | 0 | 0 | 0 | 0
10. Print Full Size Laminated Single Line & P&ID Plots | [14 empty] | 0 | 0 | 0 | 0
SUBTOTAL HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0
SUBTOTAL FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0
ADDITIONAL WORK ALLOWANCE
Additional Work Allowance |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 75000 | 75000
TOTAL PROJECT HOURS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PROJECT FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 75000 | 75000